## Summary
<insert logo here>
Sub-programme: | xxx | [6 empty] | Schedule report
Project Title: | xxx
AW Project Ref: | xxx | [6 empty] | Summary
Client Project Manager: | xxx
Current stage: | xxx | [6 empty] | Reporting Month: | 2012-08-01
[7 empty] | Date prepared: | 2012-08-31
[7 empty] | Prepared by: | xxx
[7 empty] | Distributed to: | xxx
[7 empty] | Change | Target
Earned Value Metrics |  |  | Target | 2012-06-06 | 2012-07-04 | 2012-08-01 | Down/Up | Down/Up
Planned Value (Cumulative) |  |  |  | 11571.365 | 11862.084 | 12191.328 | 329.244
Earned Value (Cumulative) |  |  |  | 6362.479 | 8003.078 | 9155.993 | 1152.915
Actual Costs (Cumulative) |  |  |  | 6623.178 | 8265.892 | 9325.712 | 1059.82
SPI |  |  | 1 | 0.54985 | 0.67468 | 0.75103 | 0.076348 | -0.24897
CPI |  |  | 1 | 0.96064 | 0.96821 | 0.9818 | 0.0075666 | -0.031795
Forecast Completion
Scheduled Project Completion |  |  | 2012-09-21 | 2013-01-03 | 2013-01-14 | 2013-01-31 | 17 | 132
Probabilistic Project Completion (P50) |  |  |  | 2013-05-15 | 2013-02-13 | 2013-03-11 | 26
Probabilistic Project Completion (P80) |  |  |  | 2013-06-25 | 2013-03-11 | 2013-04-04 | 24
Monthly Schedule Adherence Metrics
%age Activities completed on time or early |  |  | 75% | 50% | 43.24% | 49.48% | 6.241% | -25.52%
[7 empty] | Period |  | Planned Progress | Actual Progress
[7 empty] | to 24th Feb |  | 52 | 26
[7 empty] | to 23rd Mar |  | 36 | 19
[7 empty] | to 24th Apr |  | 45 | 22
[7 empty] | to 25th May |  | 46 | 22
[7 empty] | to 29th Jun |  | 52 | 25
[7 empty] | to 29th Jun |  | 52 | 25
[7 empty] | to 27th Jul |  | 26 | 15
[7 empty] | to 31st Aug |  | 22 | 9
Period | Planned Progress |  |  | Actual Progress |  |  | Period |  | Planned Progress | Actual Progress
to 29th Jun |  | 25 |  | 21 |  |  | to 29th Jun |  | 23 | 19
to 29th Jun |  | 31 |  | 24 |  |  | to 29th Jun |  | 37 | 32
to 27th Jul |  | 23 |  | 21 |  |  | to 27th Jul |  | 48 | 35
to 31st Aug |  | 19 |  | 12 |  |  | to 31st Aug |  | 56 | 27
Earned Value
SPI & CPI
Monthly Forecast Variance
Forecast Completion
Monthly Milestone Tracking
Civil Site Deliverables
M&E Site Deliverables
Procurement Deliverables

## Commentary
<insert logo here>
Sub-programme: | xxx |  | Schedule report
Title: | xxx
AW Project Ref: | xxx |  | Summary
Client Project Manager: | xxx
Current stage: | xxx |  | Reporting Month: | 2012-08-01
|  | Date prepared: | 2012-08-31
|  | Prepared by: | xxx
|  | Distributed to: | xxx
Key Milestones
All MCCs now delivered and installed, but associated software will not arrive until Sep & Oct
Recommissioning of the first Sludge Holding tank has been completed. The final two tanks should be completed in September.
Commissioning of new GBTs has been delayed to early October, due to Ops requiring a longer proving period than anticipated
Blend Tank #1 delayed, as not required until Dewatering centrifuges are in operation
Key Actions for next period
Procurement:
1) Place orders / subcontracts for: Prefab tank, Lightning Protection, lagging & trace heating, landscaping
2) Delivery of: Conveyors, Remaining Valves, Tanker Import Logger, Building Ventilation, Wesso Valve enclosures, Digester 3-way valves, Liquid & Powder poly, Actuated valves for Aeration lane, Odour Control
M&E:
1) Operating Philosophy for Aeration Lane air system
2) Complete mech & elec design for PST Autodesludging
3) Ongoing approval of vendor drawings
Civil Design:
1) Pipework supports
2) Tanker Bays
3) footpaths & roads (pending site confirmation of scope)
Site Works
Area 1: Sludge Holding Tank pipework, repair & recommissioning of Tanks 4&5, Installation of SAS system (pumps & pipework), Installation of centrifuge pumps & poly
Area 3: pipe & valve installation
Area 5: Waste Gas Burner pipework
Area 6: Delivery & installation of remaining equipment, services connections, pipework & electrical installation
Area 7: cable pulling
Area 8: Centrifuge pumps, poly & pipework
Area 9: ACWA M&E install & start of commissioning
Area 11: Booster pump installation
Slippages in Month
The following orders were not placed as planned:
-M40 prefab tank (req raised, new supplier to be setup with accounts)
The following vendor details were not received as planned:
-M03 Boilers (minor queries regarding handrails & access platform)
The following packages were not delivered as planned:
M06 Conveyors (civls not ready), M45 Ventilation (mods to existing structure required), M59 Tanker Import Logger (non-critical, delayed to avoid congested working area)
Critical Path #1 -Zero Total Float
Deliver actuated valves for Aeration Lane
(12th Sep)
Install Valves & pipework (10th Oct)
Commission & put into service (31st Oct)
Thickening Centrifuge Commissioned (7th Nov)
Ramp up sludge thickness (21st Nov)
Process Commissioning (30th Jan 13)
Gateway 5 (31st Jan 13)
Critical Path #2- 3d Float
Install Software -MCC4 (15th Oct)
SAT MCC4 (26th Oct)
Wet Commission HpH plant with FE (16th Nov)
…feeds into Process Commissioning...
Critical Path #3 - 6d Float
Progress mech Install of Boiler House(10th Sep)
Elec install of Boiler House (9th Oct)
SAT LVDB (23rd Oct)
Commission Steam System (23rd Oct)
…feeds into Wet Commission HpH plant with FE...
Key Risks to Schedule:
Threat to timely delivery of BASF Liquid & Powder poly systems -Supplier not responding to requests for completion date. Temp plant may be required to maintain programme. Required to commission centrifuges.
New scope added/agreed ref mods to ASP air distribution. -Installation methodology identified to accelerate work, leadtime of valves means system unlikely to be commissioned before October, which will delay operation of thickening centrifuge and hence commissioning of HpH -temp measures such as tankering centrates away being investigated
Condition of existing SHTs worse than expected. -Extent of repair work will not be known until Tank 5 is drained and cleaned, but average to date is additional 2 weeks of repair work.
Concerns over progress on software development for MCCs / SCADA. Should have been loaded onto MCCs for delivery, but this will not be the case. Subcontractor has committed to delivery in Sep & Oct, but are reluctant to provide regular progress updates.
Natural Gas supply -Works substantially complete, but subcontractor not responding to requests for final completion date. Required for commissioning boiler house.
Potable water supply -AWS have yet to gain approval from council for easement to install pipework in verge. Required for commissioning boiler house.

## Key_Milestones
KEY MILESTONES:
Key Milestones | CIG Baseline (GW3) | Lean Baseline (Nov 11) | Actual / Forecast | Notes
Gateway 2 | 2011-03-01 | 2011-03-01 | 2011-03-01
Gateway 3 | 2011-04-26 | 2011-04-26 | 2011-04-26
Gateway 4 (Project Wide) | 2012-08-22 | 2012-10-01 | 2012-11-22
Gateway 5 (Project Wide) | 2012-10-30 | 2012-12-07 | 2013-01-31
Gateway 6 | N/A | 2013-03-08 | 2013-05-03
Sectional Completions (GW4 dates)
SDT#1 as Post-Digestion Tank | 2012-04-25 | 2012-05-17 | 2012-07-20 | Late design info delayed pipework fabrication.
SHT#3 as Digester Feed Tank | 2012-05-15 | 2012-05-29 | 2012-08-13 | SHTs require repairing before recommissioning -not planned for. Additional delays to mech install pipe support designs
SHT#4 as Strainpress Feed Tank | 2012-07-11 | 2012-07-24 | 2012-09-04 | SHTs require repairing before recommissioning -not planned for
SHT#5 as Strainpress Feed Tank | 2012-08-22 | 2012-09-05 | 2012-09-21 | SHTs require repairing before recommissioning -not planned for
New GBTs | N/A | 2012-05-09 | 2012-10-04 | Not in GW3 scope. Delays to mech install of pipework & poly system
PST Autodesludging | N/A | N/A | 2012-10-19 | Not in baseline scope
Odour Control | 2012-07-13 | 2012-08-09 | 2012-11-02 | Late design info from vendors is delaying civils
Service Water System | 2012-06-29 | 2012-07-26 | 2012-10-26 | Late procurement of booster set
Blend Tank#1 as Centrate Well | 2011-12-13 | 2012-02-03 | 2012-09-13 | Baseline logic incorrect -requires Post-Dig in service first. Delayed further due to design finalisation of associated pipework
Aeration Lane air System | N/A | N/A | 2012-10-31 | Not in baseline scope. Better info on leadtimes for valves & installation sequence now indicate end Oct completion.
Dewatering Plant | 2012-07-13 | 2012-08-09 | 2012-11-02 | Delays to MCC Software controlling dewatering plant
Liquor Treatment Plant | 2012-08-21 | 2012-09-05 | 2012-11-15 | Cabling & containment work started late
Boiler House | 2012-07-06 | 2012-07-26 | 2012-10-26 | Delays to Torishima delivery & design info for pipework fab
Thickening Centrifuges | 2012-08-01 | 2012-08-24 | 2012-11-07 | temp poly plant may be required to mitigate supplier delays. Commissioning linked to completion of works on Aeration Lane above
Siloxane Plant | 2012-06-28 | 2012-08-30 | 2012-11-15 | Low priority, hence pushed to back of programme

## Deliverables Tracking
Discipline | Period | Area | Deliverable | Completed
Civil | to 1st July | 0 | Vehicle tracking for all Road Layouts
Civil | to 1st July | 0 | Drainage -Main Spine
Civil | to 1st July | 0 | Drainage -HPH
Civil | to 1st July | 1 | Drum Thickener Floor Plan GA Drawing (Level 2)
Civil | to 1st July | 1 | Centrifuge GA Drawing (for Approval)
Civil | to 1st July | 1 | Strainpress GA Drawing (for Approval)
Civil | to 1st July | 1 | Strainpress Structural Design
Civil | to 1st July | 3 | Hardstanding / Access Rd GA Drawing (For Approval)
Civil | to 1st July | 3 | Hardstanding / Access Rd Structural Design
Civil | to 1st July | 3 | Hardstanding / Access Rd GA Drawing (for Construction)
Civil | to 1st July | 3 | Pre treatment Tanks slab column layout and details (For Approval)
Civil | to 1st July | 3 | Hydrolysis Tank slab column layout and details (For Approval)
Civil | to 1st July | 3 | Slab GA Drawing (For Approval)
Civil | to 1st July | 3 | Slab Sections and Details (For Approval)
Civil | to 1st July | 3 | Slab GA Drawing (For Construction)
Civil | to 1st July | 3 | Slab Sections and Details (For Construction)
Civil | to 1st July | 8 | Centrifuge GA Drawing (for Approval)
Civil | to 1st July | 9 | Hydraulic Calculation -RL Gravity Pipeline 2
Civil | to 1st July | 9 | Heat Exchanger GA Drawing (for Approval)
M&E | to 1st July | 99 | Power Distribution schematic drawings
M&E | to 1st July | 99 | Basis of Design - Electrical
M&E | to 1st July | 99 | Basis of Design
M&E | to 1st July | 1 | Data Sheet: Liquid Polymer Make up system -Centrifuges (M16)
M&E | to 1st July | 1 | Spec: Liquid Polymer Make up system -Centrifuges (M16)
M&E | to 1st July | 1 | Data Sheet: Polymer Dosing Pumps -Centrifuges (M16)
M&E | to 1st July | 1 | Spec: Polymer Dosing Pumps -Centrifuges (M16)
M&E | to 1st July | 1 | Technical Assesment: Existing GBT's Primary & Imported Sludge Thickening Process (R01)
M&E | to 1st July | 3 | Basis of Design - Electrical
M&E | to 1st July | 3 | Control Philosophy
M&E | to 1st July | 3 | Data Sheet: Steam Heating Units (Direct steam injection into sludge) (M35)
M&E | to 1st July | 3 | Data Sheet: Hydrolysis Tank FE heat exchanger (M10)
M&E | to 1st July | 3 | Data Sheet: HPH Tanks V & PRV valves (M62)
M&E | to 1st July | 3 | Technical Assesment: Pasteurisation Tanks (M09)
M&E | to 1st July | 3 | Technical Assesment: Hydrolysis Tank (M09)
M&E | to 1st July | 3 | Technical Assesment: Hydrolysis Buffer Tank (Overflow tank) (M09)
M&E | to 1st July | 3 | Technical Assesment: Hydrolysis Buffer Tank Mixing (M11)
M&E | to 1st July | 3 | Technical Assesment: Pasteurisation Tank Mixing (M11)
M&E | to 1st July | 3 | Technical Assesment: Hydrolysis Tank Mixing (M11)
M&E | to 1st July | 4 | Data Sheet: Pressure/Vacuum relief system - Digester 1/Digester 2 (M62)
M&E | to 1st July | 6 | UPDWS - Boiler Water Feed Tank/Dosing (M30 & M31)
M&E | to 1st July | 6 | Data Sheet: Water Treatment Plant (Softening/Filtration/RO) (M28)
M&E | to 1st July | 6 | Data Sheet: Boiler water feed tank inc de-aerator and chemical dosing (M30 & M31)
M&E | to 1st July | 6 | Spec: Natural Gas Auto Shut-off Valve (not in DMS) (M68)
M&E | to 1st July | 6 | Technical Assesment: Composite Waste Heat Boilers (M03)
M&E | to 1st July | 8 | Data Sheet: DIGESTED SLUDGE BLOWERS (M60)
M&E | to 1st July | 8 | Data Sheet: SHARON feed tank (not in DMS) (M40)
M&E | to 1st July | 10 | Data Sheet: SILOXANE REMOVAL PACKAGE PLANT (M56)
M&E | to 1st July | 13 | UPDWS - OCS's (M43)
M&E | to 1st July | 13 | Data Sheet: Odour Treatment Plant #1 (M43)
M&E | to 1st July | 13 | Data Sheet: Odour Treatment Plant #2 (M43)
M&E | to 1st July | 13 | Spec: Odour Treatment Plant #1 (M43)
M&E | to 1st July | 13 | Spec: Odour ductwork (M43)
M&E | to 1st July | 13 | Spec: Odour Treatment Plant #2 (M43)
M&E | to 1st July | 13 | Spec: Odour ductwork (M43)
Proc | to 1st July | 99 | Prepare Enquiry Package - M04 | Y
Proc | to 1st July | 99 | Prepare Enquiry Package - M06 | Y
Proc | to 1st July | 99 | Prepare Enquiry Package - M10 | Y
Proc | to 1st July | 99 | Prepare Enquiry Package - M62
Proc | to 1st July | 1 | Prepare Enquiry Package - M16
Proc | to 1st July | 1 | Tender Duration - R01
Proc | to 1st July | 1 | Prepare Enquiry Package - R06
Proc | to 1st July | 1 | Prepare Enquiry Package - M14
Proc | to 1st July | 3 | Tender Duration - M11 | Y
Proc | to 1st July | 3 | Prepare Enquiry Package - M35
Proc | to 1st July | 5 | Prepare Enquiry Package - M24
Proc | to 1st July | 6 | Prepare Enquiry Package - M25
Proc | to 1st July | 6 | Prepare Enquiry Package - M28
Proc | to 1st July | 6 | Prepare Enquiry Package - M30
Proc | to 1st July | 6 | Prepare Enquiry Package - M31
Proc | to 1st July | 8 | Prepare Enquiry Package - M48
Proc | to 1st July | M71 | Prepare Enquiry Package - M71 | Y
Proc | to 1st July | 99 | Tender Duration -M04 | Y
Proc | to 1st July | 1 | Tender Duration -M05 | Y
Proc | to 1st July | 9 | Tender Duration -M66
Proc | to 26th August | 99 | Tender Duration -M04 | Y
Proc | to 26th August | 9 | Tender Duration -M66 | Y
Civil | to 26th August | 1 | Centrifuge GA Drawing (for Approval) | Y
Civil | to 26th August | 3 | Hardstanding / Access Rd GA Drawing (For Approval) | Y
Civil | to 26th August | 3 | Slab GA Drawing (For Approval) | Y
Civil | to 26th August | 3 | Slab Sections and Details (For Approval) | Y
Civil | to 26th August | 8 | Centrifuge GA Drawing (for Approval) | Y
M&E | to 26th August | 99 | Basis of Design | Y
M&E | to 26th August | 99 | Basis of Design - Electrical | Y
M&E | to 26th August | 1 | Data Sheet: Liquid Polymer Make up system -Centrifuges (M16) | Y
M&E | to 26th August | 1 | Data Sheet: Polymer Dosing Pumps -Centrifuges (M16) | Y
M&E | to 26th August | 1 | Spec: Liquid Polymer Make up system -Centrifuges (M16) | Y
M&E | to 26th August | 1 | Spec: Polymer Dosing Pumps -Centrifuges (M16) | Y
M&E | to 26th August | 3 | Basis of Design - Electrical | Y
M&E | to 26th August | 3 | Data Sheet: Steam Heating Units (Direct steam injection into sludge) (M35) | Y
M&E | to 26th August | 3 | Data Sheet: Hydrolysis Tank FE heat exchanger (M10) | Y
M&E | to 26th August | 3 | Data Sheet: HPH Tanks V & PRV valves (M62) | Y
M&E | to 26th August | 3 | Technical Assesment: Pasteurisation Tanks (M09) | Y
M&E | to 26th August | 3 | Technical Assesment: Hydrolysis Tank (M09) | Y
M&E | to 26th August | 3 | Technical Assesment: Hydrolysis Buffer Tank (Overflow tank) (M09) | Y
M&E | to 26th August | 3 | Technical Assesment: Hydrolysis Buffer Tank Mixing (M11) | Y
M&E | to 26th August | 3 | Technical Assesment: Pasteurisation Tank Mixing (M11) | Y
M&E | to 26th August | 3 | Technical Assesment: Hydrolysis Tank Mixing (M11) | Y
M&E | to 26th August | 4 | Data Sheet: Pressure/Vacuum relief system - Digester 1/Digester 2 (M62) | Y
M&E | to 26th August | 6 | UPDWS - Boiler Water Feed Tank/Dosing (M30 & M31) | Y
M&E | to 26th August | 6 | Data Sheet: Water Treatment Plant (Softening/Filtration/RO) (M28) | Y
M&E | to 26th August | 6 | Data Sheet: Boiler water feed tank inc de-aerator and chemical dosing (M30 & M31) | Y
M&E | to 26th August | 6 | Technical Assesment: Composite Waste Heat Boilers (M03) | Y
M&E | to 26th August | 13 | Data Sheet: Odour Treatment Plant #1 (M43) | Y
M&E | to 26th August | 13 | Data Sheet: Odour Treatment Plant #2 (M43) | Y
M&E | to 26th August | 13 | Spec: Odour Treatment Plant #1 (M43) | Y
M&E | to 26th August | 13 | Spec: Odour ductwork (M43) | Y
M&E | to 26th August | 13 | Spec: Odour Treatment Plant #2 (M43) | Y
M&E | to 26th August | 13 | Spec: Odour ductwork (M43) | Y
Proc | to 26th August | 5 | Prepare Enquiry Package - M24 | Y
Proc | to 26th August | 6 | Prepare Enquiry Package - M25 | Y
M&E | to 1st July | 1 | UPDWS -Sludge Strainpress | Y
M&E | to 1st July | 1 | Spec: Dewatered/Blended Sludge Transfer Pumps (HPH Feed Pumps) (M71) | Y
M&E | to 1st July | 4 | Spec: Pressure/Vacuum relief system - Digester 1/Digester 2 (M62) | Y
M&E | to 1st July | 5 | Data Sheet: Flare stack/gas burner package (M24) | Y
M&E | to 1st July | 5 | Spec: Flare stack/gas burner package (M24) | Y
M&E | to 1st July | 6 | UPDWS - Boiler Water Treatment (M28) | Y
M&E | to 1st July | 6 | Data Sheet: Easiheat HX unit | Y
M&E | to 1st July | 6 | Data Sheet: Fuel Oil Storgae Tank | Y
M&E | to 1st July | 6 | Spec: Flue gas system and windshield exhaust stack (M25) | Y
M&E | to 1st July | 6 | Spec: Water Treatment Plant (Softening/Filtration/RO) (M28) | Y
M&E | to 1st July | 6 | Spec: Boiler water feed tank inc de-aerator and chemical dosing (M30 & M31) | Y
M&E | to 1st July | 8 | Data Sheet: Fixed Inclined Conveyor (M06) | Y
M&E | to 1st July | 8 | Data Sheet: Bulk powder polyelectrolyte mechanical handling and storage system (M48) | Y
M&E | to 1st July | 8 | Data Sheet: Powder polmer make up and dosing system | Y
M&E | to 1st July | 8 | Spec: Bulk powder polyelectrolyte mechanical handling and storage system (M48) | Y
M&E | to 1st July | 8 | Spec: Fixed Inclined Conveyor (M06) | Y
M&E | to 1st July | 8 | Spec: Powder polmer make up and dosing system | Y
Proc | to 1st July | 99 | Tender Duration -M10 | Y
Civil | to 26th August | 0 | Drainage -Main Spine
Civil | to 26th August | 0 | Drainage -HPH
Civil | to 26th August | 1 | Centrifuge GA Drawing (for Constructionl)
Civil | to 26th August | 1 | Centrifuge RCD Drawing
Civil | to 26th August | 1 | Poly Bund GA Drawing (for Approval)
Civil | to 26th August | 1 | Cake Storage Bund Sections and Details Drawing (For Approval)
Civil | to 26th August | 1 | Cake Storage Bund Layout GA Drawing (For Approval)
Civil | to 26th August | 1 | Cake Storage Bund Layout GA Drawing (For Construction)
Civil | to 26th August | 1 | Cake Storage Bund Sections and Details Drawing (For Construction)
Civil | to 26th August | 1 | Cake Storage Bund RCD Drawing
Civil | to 26th August | 1 | Strainpress GA Drawing (for Approval)
Civil | to 26th August | 1 | Strainpress GA Drawing (for Construction)
Civil | to 26th August | 1 | Strainpress RCD Drawing
Civil | to 26th August | 3 | Hardstanding / Access Rd GA Drawing (for Construction)
Civil | to 26th August | 3 | Slab Sections and Details (For Construction)
Civil | to 26th August | 8 | Centrifuge GA Drawing (for Construction)
Civil | to 26th August | 8 | Centrifuge RCD Drawing
Civil | to 26th August | 8 | Conveyor GA Drawing (for Approval)
Civil | to 26th August | 9 | RL Gravity Pipeline 1 Longsection Drawing (Approval)
Civil | to 26th August | 9 | RL Gravity Pipeline 1 Longsection Drawing (Construction)
Civil | to 26th August | 9 | RL Gravity Pipeline 2 Longsection Drawing (Approval)
Civil | to 26th August | 9 | RL Gravity Pipeline 2 Longsection Drawing (Construction)
Civil | to 26th August | 10 | Siloxane plant GA Drawing (Approval)
M&E | to 26th August | 99 | Particular Specification Electrical Cabling | Y
M&E | to 26th August | 1 | Data Sheet: Centrifuge Feed pumps (M13)
M&E | to 26th August | 1 | Data Sheet: SAS Sludge Screen (Strainpress) Feed Pumps (M18)
M&E | to 26th August | 1 | Tender Eval: Centrifuges (inc acoustic covers) (M04)
M&E | to 26th August | 1 | Tender Eval: Chute/Hopper for Blending cake & thickened sludge (M04)
M&E | to 26th August | 1 | Tender Eval: Liquid/Solids seperator conveyor (M06)
M&E | to 26th August | 1 | Tender Eval: Liquid Polymer Make up system (M16)
M&E | to 26th August | 1 | Tender Eval: Dewatered/Blended Sludge Transfer Pumps (HPH Feed Pumps) (M71)
M&E | to 26th August | 1 | Tender Eval: Existing GBT's Primary & Imported Sludge Thickening Process (R01)
M&E | to 26th August | 1 | Tender Eval: Polymer Dosing Pumps (M16)
M&E | to 26th August | 1 | Tender Eval: Active Polymer Make up system mods (R06)
M&E | to 26th August | 1 | Tender Eval: Polymer Dosing Pump mods (R06)
M&E | to 26th August | 3 | Data Sheet: Heat Exchanger Water Recirculation Pumps (M26)
M&E | to 26th August | 3 | Data Sheet: Pasteurisation Tank Feed Pumps (M13)
M&E | to 26th August | 3 | Data Sheet: 2nd Stage Heating Sludge Recirculation Pumps(also transfers sludge to Hydrolysis Tank) (M18)
M&E | to 26th August | 3 | Data Sheet: Heat Exchanger Sludge Recirculation Pumps (M18)
M&E | to 26th August | 3 | Data Sheet: Hydrolysis HX Recirculation Pumps (M26)
M&E | to 26th August | 3 | Data Sheet: Digester Feed Pumps (part of HPH Plant) (M13)
M&E | to 26th August | 3 | Technical Assesment: LTHW Sludge/Water Heat Exchanger (M10)
M&E | to 26th August | 3 | Technical Assesment: Hydrolysis Tank FE heat exchanger (M10)
M&E | to 26th August | 3 | Technical Assesment: HPH Tanks V & PRV valves (M62)
M&E | to 26th August | 3 | Technical Assesment: Steam Heating Units (Direct steam injection into sludge) (M35)
M&E | to 26th August | 4 | UPDWS -Digester Mixing | Y
M&E | to 26th August | 5 | Technical Assesment: Flare stack/gas burner package (M24)
M&E | to 26th August | 6 | Data Sheet: Hot Water System De Aerator (not in DMS) (M65)
M&E | to 26th August | 6 | Spec: Easiheat HX unit | Y
M&E | to 26th August | 6 | Spec: Natural Gas Auto Shut-off Valve (not in DMS) (M68)
M&E | to 26th August | 6 | Technical Assesment: Flue gas system and windshield exhaust stack (M25)
M&E | to 26th August | 6 | Technical Assesment: Water Treatment Plant (Softening/Filtration/RO) (M28)
M&E | to 26th August | 6 | Technical Assesment: Boiler water feed tank inc de-aerator and chemical dosing (M30 & M31)
M&E | to 26th August | 8 | Data Sheet: OUTLET CHUTES (M12) | Y
M&E | to 26th August | 8 | Data Sheet: DIGESTED SLUDGE BLOWERS (M60)
M&E | to 26th August | 8 | Data Sheet: SHARON feed tank (not in DMS) (M40)
M&E | to 26th August | 8 | Spec: Poly dosing pumps | Y
M&E | to 26th August | 8 | Technical Assesment: CENTRIFUGES (M04)
M&E | to 26th August | 8 | Technical Assesment: Outlet Chutes (M12)
M&E | to 26th August | 8 | Technical Assesment: Fixed Inclined Conveyor (M06)
M&E | to 26th August | 8 | Technical Assesment: Bulk powder polyelectrolyte mechanical handling and storage system (M48)
M&E | to 26th August | 9 | Technical Assesment: HEAT EXCHANGER (M10)
M&E | to 26th August | 10 | Data Sheet: SILOXANE REMOVAL PACKAGE PLANT (M56)
M&E | to 26th August | 10 | Spec: SILOXANE REMOVAL PACKAGE PLANT (M56)
M&E | to 26th August | 10 | Technical Assesment: SILOXANE REMOVAL PACKAGE PLANT (M56)
Proc | to 26th August | 99 | Place Order on DEMA - M04
Proc | to 26th August | 99 | Prepare Enquiry Package - M06 | Y
Proc | to 26th August | 99 | Tender Duration - M06 | Y
Proc | to 26th August | 99 | Tender Duration - M10 | Y
Proc | to 26th August | 99 | Place Order on DEMA - M10
Proc | to 26th August | 99 | Prepare Enquiry Package - M62
Proc | to 26th August | 99 | Tender Duration - M62
Proc | to 26th August | 99 | Place Order on DEMA - M62
Proc | to 26th August | 1 | Prepare Enquiry Package - M14
Proc | to 26th August | 1 | Tender Duration - M14
Proc | to 26th August | 1 | Place Order on DEMA - M14
Proc | to 26th August | 1 | Prepare Enquiry Package - M16
Proc | to 26th August | 1 | Tender Duration - M16
Proc | to 26th August | 1 | Prepare Enquiry Package - R06
Proc | to 26th August | 1 | Tender Duration - R06
Proc | to 26th August | 3 | Tender Duration - M11 | Y
Proc | to 26th August | 3 | Place Order on DEMA - M11
Proc | to 26th August | 3 | Prepare Enquiry Package - M35
Proc | to 26th August | 3 | Tender Duration - M35
Proc | to 26th August | 3 | Tender Duration - M71 | Y
Proc | to 26th August | 3 | Place Order on DEMA - M71
Proc | to 26th August | 5 | Tender Duration - M24 | Y
Proc | to 26th August | 5 | Place Order on DEMA - M24
Proc | to 26th August | 6 | Place Order on DEMA - M03
Proc | to 26th August | 6 | Tender Duration - M25
Proc | to 26th August | 6 | Prepare Enquiry Package - M28
Proc | to 26th August | 6 | Tender Duration - M28
Proc | to 26th August | 6 | Prepare Enquiry Package - M30
Proc | to 26th August | 6 | Tender Duration - M30
Proc | to 26th August | 6 | Prepare Enquiry Package - M31
Proc | to 26th August | 6 | Tender Duration - M31
Proc | to 26th August | 6 | Prepare Enquiry Package - M65
Proc | to 26th August | 6 | Prepare Enquiry Package - M68
Proc | to 26th August | 6 | Tender Duration - M68
Proc | to 26th August | 7 | Prepare Enquiry Package - E05
Proc | to 26th August | 8 | Prepare Enquiry Package - M48
Proc | to 26th August | 8 | Tender Duration - M48
Proc | to 26th August | 9 | Place Order on DEMA - M66
Proc | to 26th August | 10 | Prepare Enquiry Package - M56
Proc | to 26th August | 10 | Tender Duration - M56
M&E | to 26th August | 99 | Particular Specification MCC & Associated Equip. | Y
M&E | to 26th August | 99 | Spec: Electrical Installation - General | Y
M&E | to 26th August | 1 | Data Sheet: Blending Tank Mixing (Cakedilution) Pump (M13) | Y
M&E | to 26th August | 1 | Spec: MCC inc ICA (E03) | Y
M&E | to 26th August | 1 | Spec: Electrical Installation | Y
M&E | to 26th August | 3 | Spec: MCC inc ICA (E03) | Y
M&E | to 26th August | 3 | Spec: Electrical Installation | Y
M&E | to 26th August | 5 | Spec: Electrical Installation | Y
M&E | to 26th August | 6 | Spec: Electrical Installation | Y
M&E | to 26th August | 6 | Spec: MCC inc ICA | Y
M&E | to 26th August | 8 | Spec: MCC inc ICA | Y
M&E | to 26th August | 8 | Spec: Electrical Installation | Y
M&E | to 26th August | 9 | Spec: MCC inc ICA | Y
M&E | to 26th August | 9 | Spec: Electrical Installation | Y
M&E | to 26th August | 11 | Spec: Electrical Installation | Y
Proc | to 26th August | 99 | Prepare Enquiry Package - E02 | Y
Proc | to 26th August | 1 | Tender Duration - M05 | Y
Proc | to 26th August | 7 | Prepare Enquiry Package - E03 | Y
Civil | to 9th Sep | 0 | Vehicle tracking for all Road Layouts
Civil | to 9th Sep | 1 | Poly Bund GA Drawing (for Approval)
Civil | to 9th Sep | 1 | Cake Bund Sections and Details Drawing (For Approval)
Civil | to 9th Sep | 3 | Slab GA Drawing (For Construction)
Civil | to 9th Sep | 3 | RCD Drawing - Pre treatment Tanks
Civil | to 9th Sep | 3 | RCD Drawing - Hydrolysis Tanks
Civil | to 9th Sep | 3 | Slab Sections and Details (For Construction)
Civil | to 9th Sep | 3 | RCD Drawing - Surrounding Slab and Plant Plinths
Civil | to 9th Sep | 8 | Conveyor GA Drawing (for Approval)
Civil | to 9th Sep | 8 | Conveyor GA Drawing (for Constrcution)
Civil | to 9th Sep | 9 | RL Gravity Pipeline 1 Longsection Drawing (Approval)
Civil | to 9th Sep | 9 | RL Gravity Pipeline 1 Longsection Drawing (Constructionl)
Civil | to 9th Sep | 9 | RL Gravity Pipeline 2 Longsection Drawing (Approval)
Civil | to 9th Sep | 9 | RL Gravity Pipeline 2 Longsection Drawing (Constructionl)
Civil | to 9th Sep | 9 | Manhole GA Drawing (Approval)
Civil | to 9th Sep | 9 | Manhole GA Drawing (Construction)
M&E | to 9th Sep | 99 | Spec: Mechanical Installation - General (M12)
Proc | to 9th Sep | 99 | Place Order on DEMA - M09
M&E | to 9th Sep | 1 | Data Sheet: Centrifuge Feed pumps (M13)
M&E | to 9th Sep | 1 | Data Sheet: SAS Sludge Screen (Strainpress) Feed Pumps (M18)
M&E | to 9th Sep | 1 | IData Sheet: Isolation of redundant equipment (M12)
M&E | to 9th Sep | 1 | Spec: MCC kiosk
M&E | to 9th Sep | 1 | Technical Assesment: Centrifuges (inc acoustic covers) (M04)
M&E | to 9th Sep | 1 | Technical Assesment: Chute/Hopper for Blending cake & thickened sludge (M04)
M&E | to 9th Sep | 1 | Technical Assesment: Liquid/Solids seperator conveyor (M06)
M&E | to 9th Sep | 1 | Technical Assesment: Liquid Polymer Make up system (M16)
M&E | to 9th Sep | 1 | Technical Assesment: Dewatered/Blended Sludge Transfer Pumps (HPH Feed Pumps) (M71)
M&E | to 9th Sep | 1 | Technical Assesment: Existing GBT's Primary & Imported Sludge Thickening Process (R01)
M&E | to 9th Sep | 3 | Heat Exchanger Water Recirculation Pumps (M26)
M&E | to 9th Sep | 3 | Data Sheets: Pasteurisation Tank Feed Pumps (M13)
M&E | to 9th Sep | 3 | Data Sheets: 2nd Stage Heating Sludge Recirculation Pumps(also transfers sludge to Hydrolysis Tank) (M18)
M&E | to 9th Sep | 3 | Data Sheets: Heat Exchanger Sludge Recirculation Pumps (M18)
M&E | to 9th Sep | 3 | Data Sheets: Hydrolysis HX Recirculation Pumps (M26)
M&E | to 9th Sep | 3 | Technical Assesment: LTHW Sludge/Water Heat Exchanger (M10)
M&E | to 9th Sep | 3 | Technical Assesment: Hydrolysis Tank FE heat exchanger (M10)
M&E | to 9th Sep | 3 | Technical Assesment: HPH Tanks V & PRV valves (M62)
M&E | to 9th Sep | 5 | Technical Assesment: Flare stack/gas burner package (M24)
M&E | to 9th Sep | 6 | Data Sheet: Hot water recirculation pumps - Motive Water system (M26)
M&E | to 9th Sep | 6 | Data Sheet: Hot water recirculation pumps - CHP heat exchange (M26)
M&E | to 9th Sep | 6 | Spec: Natural Gas Auto Shut-off Valve (not in DMS) (M68)
M&E | to 9th Sep | 8 | Data Sheet: Leaf Spring DIFFUSERS (M12)
M&E | to 9th Sep | 8 | Data Sheet: DIGESTED SLUDGE BLOWERS (M60)
M&E | to 9th Sep | 8 | Data Sheet: SHARON feed tank (not in DMS) (M40)
M&E | to 9th Sep | 8 | Data Sheet: Centrifuge Feed Pumps (M13)
M&E | to 9th Sep | 8 | Spec: SHARON feed tank (not in DMS) (M40)
M&E | to 9th Sep | 8 | Technical Assesment: CENTRIFUGES (M04)
M&E | to 9th Sep | 8 | Technical Assesment: Outlet Chutes (M12)
M&E | to 9th Sep | 8 | Technical Assesment: Fixed Inclined Conveyor (M06)
M&E | to 9th Sep | 9 | Spec: MCC kiosk
M&E | to 9th Sep | 10 | Data Sheet: SILOXANE REMOVAL PACKAGE PLANT (M56)
M&E | to 9th Sep | 10 | Spec: SILOXANE REMOVAL PACKAGE PLANT (M56)
M&E | to 9th Sep | 13 | UPDWS - OCS's (M43) | Y
M&E | to 9th Sep | 13 | Technical Assesment: Odour Treatment Plant #1 (M43)
M&E | to 9th Sep | 13 | Technical Assesment: Odour ductwork (M43)
M&E | to 9th Sep | 13 | Technical Assesment: Odour Treatment Plant #2 (M43)
M&E | to 9th Sep | 13 | Technical Assesment: Odour ductwork (M43)
Proc | to 9th Sep | 99 | Prepare Enquiry Package - M60
Proc | to 9th Sep | 99 | Prepare Enquiry Package - M62
Proc | to 9th Sep | 99 | Tender Duration - M62
Proc | to 9th Sep | 1 | Prepare Enquiry Package - M14
Proc | to 9th Sep | 1 | Tender Duration - M14
Proc | to 9th Sep | 1 | Prepare Enquiry Package - M16
Proc | to 9th Sep | 1 | Tender Duration - M16
Proc | to 9th Sep | 1 | Prepare Enquiry Package - R06
Proc | to 9th Sep | 1 | Tender Duration - R06
Proc | to 9th Sep | 3 | Place Order on DEMA - M11
Proc | to 9th Sep | 3 | Prepare Enquiry Package - M35
Proc | to 9th Sep | 3 | Tender Duration - M35
Proc | to 9th Sep | 3 | Place Order on DEMA - M71
Proc | to 9th Sep | 5 | Place Order on DEMA - M24
Proc | to 9th Sep | 6 | Tender Duration - M25
Proc | to 9th Sep | 6 | Prepare Enquiry Package - M27
Proc | to 9th Sep | 6 | Prepare Enquiry Package - M28
Proc | to 9th Sep | 6 | Tender Duration - M28
Proc | to 9th Sep | 6 | Prepare Enquiry Package - M30 | Y
Proc | to 9th Sep | 6 | Tender Duration - M30
Proc | to 9th Sep | 6 | Prepare Enquiry Package - M31
Proc | to 9th Sep | 6 | Tender Duration - M31
Proc | to 9th Sep | 6 | Prepare Enquiry Package - M68
Proc | to 9th Sep | 7 | Prepare Enquiry Package - E06
Proc | to 9th Sep | 8 | Prepare Enquiry Package - M48
Proc | to 9th Sep | 8 | Tender Duration - M48
Proc | to 9th Sep | 10 | Prepare Enquiry Package - M56
Proc | to 9th Sep | 13 | Prepare Enquiry Package - M43 | Y
Proc | to 9th Sep | 13 | Tender Duration - M43
Civil | to 5th Oct | 0 | Vehicle tracking for all Road Layouts
Civil | to 5th Oct | 0 | Drainage -Main Spine
Civil | to 5th Oct | 0 | Drainage -HPH
Civil | to 5th Oct | 1 | Poly Bund GA Drawing (for Approval)
Civil | to 5th Oct | 1 | Poly Bund Structural Design
Civil | to 5th Oct | 3 | HpH Plant hardstanding GA Drawing (For Approval) | Y
Civil | to 5th Oct | 3 | HpH Plant hardstanding Structural Design
Civil | to 5th Oct | 3 | HpH Plant hardstanding GA Drawing (For Construction)
Civil | to 5th Oct | 3 | HpH Plant Slab GA Drawing (For Construction) | Y
Civil | to 5th Oct | 3 | HpH Plant Structural Design - Surrounding Slab and Plant Plinths
Civil | to 5th Oct | 3 | HpH Plant Slab Sections and Details (For Construction)
Civil | to 5th Oct | 3 | HpH Plant RCD Drawing - Pre treatment Tanks | Y
Civil | to 5th Oct | 3 | HpH Plant RCD Drawing - Hydrolysis Tanks | Y
Civil | to 5th Oct | 3 | HpH Plant RCD Drawing - Surrounding Slab and Plant Plinths
Civil | to 5th Oct | 6 | Flue Stack RCD drawing
Civil | to 5th Oct | 8 | Cake Bund Sections and Details Drawing (For Approval)
Civil | to 5th Oct | 8 | Cake Bund Structural Design
Civil | to 5th Oct | 8 | Cake Bund Precast / in situ wall units analysis
Civil | to 5th Oct | 9 | Return Liquors Gravity Pipeline 1 Hydraulic Calculation
Civil | to 5th Oct | 9 | Return Liquors Gravity Pipeline 1 Longsection Drawing (Approval)
Civil | to 5th Oct | 9 | Return Liquors Gravity Pipeline 1 Longsection Drawing (Construction)
Civil | to 5th Oct | 9 | Return Liquors Gravity Pipeline 2 Hydraulic Calculation
Civil | to 5th Oct | 9 | Return Liquors Gravity Pipeline 2 Longsection Drawing (Approval)
Civil | to 5th Oct | 9 | Return Liquors Gravity Pipeline 2 Longsection Drawing (Construction)
Civil | to 5th Oct | 9 | Return Liquors Gravity Pipeline 4 Hydraulic Calculation | Y
Civil | to 5th Oct | 9 | Return Liquors Gravity Pipeline 4 Longsection Drawing (Approval) | Y
Civil | to 5th Oct | 9 | Return Liquors Gravity Pipeline 4 Longsection Drawing (Construction) | Y
Civil | to 5th Oct | 9 | New manhole GA Drawing (For approval)
Civil | to 5th Oct | 9 | New manhole Structural Design
Civil | to 5th Oct | 9 | New manhole GA Drawing (For Construction)
M&E | to 5th Oct | 99 | Particular Specification MCC & Associated Equip.
M&E | to 5th Oct | 99 | Particular Specification Electrical Cabling
M&E | to 5th Oct | 99 | Particular Spec: Electrical Installation - General
M&E | to 5th Oct | 1 | Particular Spec: MCC inc ICA (E03)
M&E | to 5th Oct | 1 | Particular Spec: Electrical Installation
M&E | to 5th Oct | 1 | Tender Eval: Centrifuges (inc acoustic covers) (M04) | Y
M&E | to 5th Oct | 1 | Tender Eval: Chute/Hopper for Blending cake & thickened sludge (M04) | Y
M&E | to 5th Oct | 1 | Tender Eval: Liquid/Solids seperator conveyor (M06) | Y
M&E | to 5th Oct | 3 | Data Sheet: Heat Exchanger Water Recirculation Pumps (M26)
M&E | to 5th Oct | 3 | Data Sheet: Pasteurisation Tank Feed Pumps (M13)
M&E | to 5th Oct | 3 | Data Sheet: 2nd Stage Heating Sludge Recirculation Pumps(also transfers sludge to Hydrolysis Tank) (M18)
M&E | to 5th Oct | 3 | Particular Spec: MCC inc ICA (E03)
M&E | to 5th Oct | 3 | Particular Spec: Electrical Installation
M&E | to 5th Oct | 3 | Tender Eval: LTHW Sludge/Water Heat Exchanger (M10)
M&E | to 5th Oct | 3 | Tender Eval: Hydrolysis Tank FE heat exchanger (M10)
M&E | to 5th Oct | 3 | Pasteurisation Tanks GA (M09)
M&E | to 5th Oct | 3 | Hydrolysis Tank GA (M09)
M&E | to 5th Oct | 5 | Tender Eval: Flare stack/gas burner package (M24)
M&E | to 5th Oct | 6 | Data Sheet: Pressurisation unit (M27)
M&E | to 5th Oct | 6 | Data Sheet: Hot water recirculation pumps - Motive Water system (M26)
M&E | to 5th Oct | 6 | Data Sheet: Hot water recirculation pumps - CHP heat exchange (M26)
M&E | to 5th Oct | 6 | Particular Spec: Electrical Installation
M&E | to 5th Oct | 6 | Particular Spec: MCC inc ICA
M&E | to 5th Oct | 6 | Tender Eval: Easiheat HX
M&E | to 5th Oct | 6 | Tender Eval: Fuel oil Storage tank / Nat gas supply
M&E | to 5th Oct | 8 | Data Sheet: DIGESTED SLUDGE BLOWERS (M60)
M&E | to 5th Oct | 8 | Particular Spec: MCC inc ICA
M&E | to 5th Oct | 8 | Tender Eval: CENTRIFUGES (M04) | Y
M&E | to 5th Oct | 8 | Tender Eval: Outlet Chutes (M12) | Y
M&E | to 5th Oct | 8 | Tender Eval: Fixed Inclined Conveyor (M06)
M&E | to 5th Oct | 8 | GA: Dewatering Centrifuges (M04)
M&E | to 5th Oct | 8 | CENTRIFUGES ELEVATION & SECTION
M&E | to 5th Oct | 9 | Tender Eval: Liquor Treatment | Y
M&E | to 5th Oct | 10 | Data Sheet: SILOXANE REMOVAL PACKAGE PLANT (M56)
M&E | to 5th Oct | 10 | Particular Spec: SILOXANE REMOVAL PACKAGE PLANT (M56)
M&E | to 5th Oct | 11 | UPDWS - UV disinfection (M42)
M&E | to 5th Oct | 11 | Data Sheet: Water booster package - duty/duty/standby pumps + accumulator
M&E | to 5th Oct | 11 | Data Sheet: Water booster package - duty/duty/standby pumps + c/w accumulator & Form 4 Panel
M&E | to 5th Oct | 11 | Data Sheet: Pipeline UV System (M42)
M&E | to 5th Oct | 11 | Data Sheet: Self-cleaning Filters 300 micron (M39)
M&E | to 5th Oct | 11 | Data Sheet: Self-cleaning Filters 50 micron (M39)
M&E | to 5th Oct | 11 | Particular Spec: Water booster package - duty/duty/standby pumps + accumulator
M&E | to 5th Oct | 11 | Particular Spec: Water booster package - duty/duty/standby pumps + c/w accumulator & Form 4 Panel
M&E | to 5th Oct | 11 | Particular Spec: Self-cleaning Filters 300 micron (M39)
M&E | to 5th Oct | 11 | Particular Spec: Self-cleaning Filters 50 micron (M39)
M&E | to 5th Oct | 11 | Particular Spec: Pipeline UV System (M42)
M&E | to 5th Oct | 11 | Tender Eval: Odour Treatment Plant #1 (M43)
M&E | to 5th Oct | 11 | Tender Eval: Odour Treatment Plant #2 (M43)
M&E | to 5th Oct | 11 | Tender Eval: Odour ductwork #1 (M43)
M&E | to 5th Oct | 11 | Tender Eval: Odour ductwork #2 (M43)
Proc | to 5th Oct | 99 | Prepare Enquiry Package - M62
Proc | to 5th Oct | 99 | Prepare Enquiry Package - E13 | Y
Proc | to 5th Oct | 99 | Prepare Enquiry Package - E16 | Y
Proc | to 5th Oct | 99 | Prepare Enquiry Package - E17 | Y
Proc | to 5th Oct | 99 | Prepare Enquiry Package - E19 | Y
Proc | to 5th Oct | 99 | Prepare Enquiry Package - E20 | Y
Proc | to 5th Oct | 99 | Prepare Enquiry Package - E21 | Y
Proc | to 5th Oct | 99 | Prepare Enquiry Package - E22 | Y
Proc | to 5th Oct | 99 | Prepare Enquiry Package - E23 | Y
Proc | to 5th Oct | 1 | Prepare Enquiry Package - M14
Proc | to 5th Oct | 1 | Prepare Enquiry Package - M16 | Y
Proc | to 5th Oct | 1 | Prepare Enquiry Package - R06
Proc | to 5th Oct | 3 | Prepare Enquiry Package - M35 | Y
Proc | to 5th Oct | 6 | Prepare Enquiry Package - M28
Proc | to 5th Oct | 6 | Prepare Enquiry Package - M31
Proc | to 5th Oct | 8 | Prepare Enquiry Package - M48 | Y
Proc | to 5th Oct | 10 | Prepare Enquiry Package - M56
Proc | to 5th Oct | 11 | Prepare Enquiry Package - M42
M&E | to 9th Sep | 3 | External review of design | Y
M&E | to 9th Sep | 6 | PFD related mass, heat and flows balance | Y
Proc | to 9th Sep | 6 | Prepare Enquiry Package - M29 | Y
Civil | to 16th Nov | 0 | Vehicle tracking for all Road Layouts
Civil | to 16th Nov | 0 | Drainage -Main Spine
Civil | to 16th Nov | 0 | Drainage -HPH
Civil | to 16th Nov | 1 | Structural Design -Centrifuges
Civil | to 16th Nov | 1 | GA Drawing (for Approval) -Centrifuges
Civil | to 16th Nov | 6 | Structural Design -Blower bldg floor mods
Civil | to 16th Nov | 6 | GA Drawing (Approval) -Blower bldg floor mods
Civil | to 16th Nov | 6 | GA Drawing (Approval) -Blower bldg wall mods
Civil | to 16th Nov | 8 | Sections and Details Drawing (For Approval) -Cake bund | Y
Civil | to 16th Nov | 8 | Structural Design -Cake bund | Y
Civil | to 16th Nov | 8 | Precast / in situ wall units analysis -Cake bund | Y
Civil | to 16th Nov | 8 | Layout GA Drawing (For Approval) -Cake bund | Y
Civil | to 16th Nov | 8 | Layout GA Drawing (For Construction) -Cake bund
Civil | to 16th Nov | 8 | Sections and Details Drawing (For Construction) -Cake bund
Civil | to 16th Nov | 8 | RCD Drawing -Cake bund
Civil | to 16th Nov | 9 | Longsection Drawing (Approval) -Pipeline 2
M&E | to 16th Nov | 99 | Instrumentation - General -Spec
M&E | to 16th Nov | 99 | Lifting Equipment - General (M47) -Spec
M&E | to 16th Nov | 99 | HazOp Study - Digesters (Area 4)
M&E | to 16th Nov | 99 | HazOp Study
M&E | to 16th Nov | 1 | Centrifuge Feed pumps (M13) -Data Sheet
M&E | to 16th Nov | 1 | SAS Sludge Screen (Strainpress) Feed Pumps (M18) -Data Sheet
M&E | to 16th Nov | 1 | Centrate Tank/Sump -Data Sheet
M&E | to 16th Nov | 1 | Centrate Pumps - return of centrate to WwTW (M18) -Data Sheet
M&E | to 16th Nov | 1 | Isolation of redundant equipment (M12) -Data Sheet
M&E | to 16th Nov | 1 | Instrumentation - level -Spec
M&E | to 16th Nov | 1 | Instrumentation - flow -Spec
M&E | to 16th Nov | 1 | Instrumentation - pressure -Spec
M&E | to 16th Nov | 1 | Instrumentation - temperature -Spec
M&E | to 16th Nov | 1 | Liquid Polymer Make up system (M16) -TAR
M&E | to 16th Nov | 1 | Instrumentation - flow -TAR
M&E | to 16th Nov | 1 | Instrumentation - pressure -TAR
M&E | to 16th Nov | 1 | Instrumentation - temperature -TAR
M&E | to 16th Nov | 1 | Dewatered/Blended Sludge Transfer Pumps (HPH Feed Pumps) (M71) -TAR | Y
M&E | to 16th Nov | 1 | Polymer Dosing Pumps (M16) -TAR
M&E | to 16th Nov | 3 | Heat Exchanger Water Recirculation Pumps (M26) -Data Sheet
M&E | to 16th Nov | 3 | Pasteurisation Tank Feed Pumps (M13) -Data Sheet
M&E | to 16th Nov | 3 | 2nd Stage Heating Sludge Recirculation Pumps(also transfers sludge to Hydrolysis Tank) (M18) -Data Sheet
M&E | to 16th Nov | 3 | Heat Exchanger Sludge Recirculation Pumps (M18) -Data Sheet
M&E | to 16th Nov | 3 | Hydrolysis HX Recirculation Pumps (M26) -Data Sheet
M&E | to 16th Nov | 3 | Digester Feed Pumps (part of HPH Plant) (M13) -Data Sheet
M&E | to 16th Nov | 3 | Instrumentation - level -Spec
M&E | to 16th Nov | 3 | Instrumentation - flow -Spec
M&E | to 16th Nov | 3 | Instrumentation - pressure -Spec
M&E | to 16th Nov | 3 | Instrumentation - temperature -Spec
M&E | to 16th Nov | 3 | LTHW Sludge/Water Heat Exchanger (M10) -TAR | Y
M&E | to 16th Nov | 3 | Hydrolysis Tank FE heat exchanger (M10)-TAR | Y
M&E | to 16th Nov | 3 | Steam Heating Units (Direct steam injection into sludge) (M35)-TAR
M&E | to 16th Nov | 3 | Instrumentation - flow-TAR
M&E | to 16th Nov | 3 | Instrumentation - pressure-TAR
M&E | to 16th Nov | 3 | Instrumentation - temperature-TAR
M&E | to 16th Nov | 3 | Pasteurisation Tanks GA (M09)
M&E | to 16th Nov | 3 | Hydrolysis Tank GA (M09)
M&E | to 16th Nov | 3 | HPH Buffer Tank GA (Overflow tank) (M09)
M&E | to 16th Nov | 3 | HPH GA
M&E | to 16th Nov | 4 | Instrumentation - level -Spec
M&E | to 16th Nov | 4 | Instrumentation - flow -Spec
M&E | to 16th Nov | 4 | Instrumentation - pressure -Spec
M&E | to 16th Nov | 4 | Instrumentation - temperature -Spec
M&E | to 16th Nov | 4 | Instrumentation - flow-TAR
M&E | to 16th Nov | 4 | Instrumentation - pressure-TAR
M&E | to 16th Nov | 4 | Instrumentation - temperature-TAR
M&E | to 16th Nov | 5 | Flare stack/gas burner package (M24) -TAR | Y
M&E | to 16th Nov | 6 | Pressurisation unit (M27) -Data Sheet
M&E | to 16th Nov | 6 | Hot water recirculation pumps - Motive Water system (M26) -Data Sheet
M&E | to 16th Nov | 6 | Hot water recirculation pumps - CHP heat exchange (M26) -Data Sheet
M&E | to 16th Nov | 6 | Instrumentation - level -Spec
M&E | to 16th Nov | 6 | Instrumentation - flow -Spec
M&E | to 16th Nov | 6 | Instrumentation - pressure -Spec
M&E | to 16th Nov | 6 | Instrumentation - temperature -Spec
M&E | to 16th Nov | 6 | Steam system components inc condensate traps (M33) -Spec
M&E | to 16th Nov | 6 | Easiheat HX -TAR
M&E | to 16th Nov | 6 | Fuel oil Storage tank / Nat gas supply -TAR
M&E | to 16th Nov | 6 | Instrumentation - flow-TAR
M&E | to 16th Nov | 6 | Instrumentation - pressure-TAR
M&E | to 16th Nov | 6 | Instrumentation - temperature-TAR
M&E | to 16th Nov | 6 | GROUND FLOOR GENERAL ARRANGEMENT ISOMETRIC VIEW
M&E | to 16th Nov | 6 | PLAN VIEW (EQUIPMENT LAYOUT)
M&E | to 16th Nov | 8 | DIGESTED SLUDGE BLOWERS (M60) -Data Sheet
M&E | to 16th Nov | 8 | Centrifuge Feed Pumps (M13) -Data Sheet
M&E | to 16th Nov | 8 | Instrumentation - level -Spec
M&E | to 16th Nov | 8 | Instrumentation - flow -Spec
M&E | to 16th Nov | 8 | Instrumentation - pressure -Spec
M&E | to 16th Nov | 8 | Instrumentation - temperature -Spec
M&E | to 16th Nov | 8 | Fixed Inclined Conveyor (M06) -TAR
M&E | to 16th Nov | 8 | Bulk powder polyelectrolyte mechanical handling and storage system (M48) -TAR
M&E | to 16th Nov | 8 | Instrumentation - flow-TAR
M&E | to 16th Nov | 8 | Instrumentation - pressure-TAR
M&E | to 16th Nov | 8 | Instrumentation - temperature-TAR
M&E | to 16th Nov | 9 | Liquor Treatment -TAR
M&E | to 16th Nov | 10 | SILOXANE REMOVAL PACKAGE PLANT (M56) -Data Sheet
M&E | to 16th Nov | 10 | SILOXANE REMOVAL PACKAGE PLANT (M56) -Spec
M&E | to 16th Nov | 11 | UPDWS - UV disinfection (M42)
M&E | to 16th Nov | 11 | Water booster package - duty/duty/standby pumps + accumulator -Data Sheet
M&E | to 16th Nov | 11 | Pipeline UV System (M42) -Data Sheet
M&E | to 16th Nov | 11 | Self-cleaning Filters 300 micron (M39) -Data Sheet | Y
M&E | to 16th Nov | 11 | Self-cleaning Filters 50 micron (M39) -Data Sheet | Y
M&E | to 16th Nov | 11 | Centrifugal Pumps (M18) -Data Sheet
M&E | to 16th Nov | 11 | Water booster package - duty/duty/standby pumps + accumulator -Spec
M&E | to 16th Nov | 11 | Self-cleaning Filters 300 micron (M39) -Spec | Y
M&E | to 16th Nov | 11 | Self-cleaning Filters 50 micron (M39) -Spec | Y
M&E | to 16th Nov | 11 | Pipeline UV System (M42) -Spec
M&E | to 16th Nov | 11 | Centrifugal Pumps (M18) -Spec
M&E | to 16th Nov | 11 | Instrumentation - level -Spec
M&E | to 16th Nov | 11 | Instrumentation - flow -Spec
M&E | to 16th Nov | 11 | Instrumentation - pressure -Spec
M&E | to 16th Nov | 11 | Instrumentation - temperature -Spec
M&E | to 16th Nov | 11 | Instrumentation - flow-TAR
M&E | to 16th Nov | 11 | Instrumentation - pressure-TAR
M&E | to 16th Nov | 11 | Instrumentation - temperature-TAR
M&E | to 16th Nov | 13 | Odour Treatment Plant #1 (M43) -TAR
M&E | to 16th Nov | 13 | Odour ductwork (M43) -TAR
M&E | to 16th Nov | 13 | Odour Treatment Plant #2 (M43) -TAR
M&E | to 16th Nov | 13 | Odour ductwork (M43) -TAR
Proc | to 16th Nov |  | Place Order on DEMA - M04
Proc | to 16th Nov |  | Place Order on DEMA - M09
Proc | to 16th Nov |  | Prepare Enquiry Package - M13 | Y
Proc | to 16th Nov |  | Prepare Enquiry Package - M60
Proc | to 16th Nov |  | Prepare Enquiry Package - M62
Proc | to 16th Nov |  | Place Order on DEMA - M05
Proc | to 16th Nov |  | Prepare Enquiry Package - M14 | Y
Proc | to 16th Nov |  | Place Order on DEMA - M11 | Y
Proc | to 16th Nov |  | Place Order on DEMA - M03
Proc | to 16th Nov |  | Prepare Enquiry Package - M28 | Y
Proc | to 16th Nov |  | Prepare Enquiry Package - M39
Proc | to 16th Nov |  | Prepare Enquiry Package - M42
Civil | to 31st Dec |  | Vehicle tracking for all Road Layouts
Civil | to 31st Dec |  | Drainage -Main Spine
Civil | to 31st Dec |  | Drainage -HPH
Civil | to 31st Dec | 1 | GA & RCD Drawing (for Construction) -Forward Pump Slab
Civil | to 31st Dec | 6 | GA Drawing (Construction) -Boiler bldg wall mods
Civil | to 31st Dec | 8 | Sections and Details Drawing (For Construction) -Cake Bund
Civil | to 31st Dec | 8 | RCD Drawing -Cake Bund
Civil | to 31st Dec | 8 | GA Drawing (for Construction) -Centrifuge
Civil | to 31st Dec | 8 | GA & RCD Drawing (for Construction) -Pump slab
Civil | to 31st Dec | 8 | GA Drawing (for Construction) -Centrifuge Feed PS
M&E | to 31st Dec | 99 | Mechanical Installation - General (M12) -Spec | Y
M&E | to 31st Dec | 99 | Instrumentation - General -Spec
M&E | to 31st Dec | 99 | Valves - General (M44) -Spec
M&E | to 31st Dec | 99 | Lifting Equipment - General (M47) -Spec
M&E | to 31st Dec | 99 | Trace Heating and Insulation - General (M46) -Spec
M&E | to 31st Dec | 99 | Electrical Installation - General -TAR
M&E | to 31st Dec | 99 | MCC's / ICA's -TAR
M&E | to 31st Dec | 99 | HazOp Study
M&E | to 31st Dec | 99 | MCC Schedule | Y
M&E | to 31st Dec | 1 | Feeder Schedule | Y
M&E | to 31st Dec | 1 | Centrifuge Feed / GBT feed pumps (M13) -Data Sheet | Y
M&E | to 31st Dec | 1 | SAS Sludge Screen (Strainpress) Feed Pumps (M18) -Data Sheet
M&E | to 31st Dec | 1 | Centrate Pumps - return of centrate to WwTW (M18) -Data Sheet
M&E | to 31st Dec | 1 | SAS Thickener Feed Pumps (M??) -Data Sheet
M&E | to 31st Dec | 1 | Isolation of redundant equipment (M12) -Data Sheet | Y
M&E | to 31st Dec | 1 | PST Autodesludging -Data Sheet
M&E | to 31st Dec | 1 | Centrate Tank/Sump -Data Sheet
M&E | to 31st Dec | 1 | Pipework (M12) -Spec | Y
M&E | to 31st Dec | 1 | Mechanical Installation (M12) -Spec | Y
M&E | to 31st Dec | 1 | MCC inc ICA (E03) -Spec | Y
M&E | to 31st Dec | 1 | MCC inc ICA -TAR
M&E | to 31st Dec | 1 | Liquid Polymer Make up system (M16) -TAR
M&E | to 31st Dec | 1 | Instrumentation - flow -TAR
M&E | to 31st Dec | 1 | Instrumentation - pressure -TAR
M&E | to 31st Dec | 1 | Instrumentation - temperature -TAR
M&E | to 31st Dec | 1 | Polymer Dosing Pumps (M16) -TAR
M&E | to 31st Dec | 1 | Electrical Installation -TAR
M&E | to 31st Dec | 1 | Centrate Pumps - return of centrate to WwTW (M18) -TAR
M&E | to 31st Dec | 1 | SAS Thickeners GA (M05)
M&E | to 31st Dec | 1 | Thickening Centrifuges (M04)
M&E | to 31st Dec | 3 | I/O Schedule SCADA System | Y
M&E | to 31st Dec | 3 | Load Schedule | Y
M&E | to 31st Dec | 3 | Cable Schedule | Y
M&E | to 31st Dec | 3 | Feeder Schedule | Y
M&E | to 31st Dec | 3 | MCC Schedule | Y
M&E | to 31st Dec | 3 | Control Philosophy | Y
M&E | to 31st Dec | 3 | Heat Exchanger Water Recirculation Pumps (M26) -Data Sheet | Y
M&E | to 31st Dec | 3 | Pasteurisation Tank Feed Pumps (M13) -Data Sheet | Y
M&E | to 31st Dec | 3 | 2nd Stage Heating Sludge Recirculation Pumps(also transfers sludge to Hydrolysis Tank) (M18) -Data Sheet
M&E | to 31st Dec | 3 | Heat Exchanger Sludge Recirculation Pumps (M18) -Data Sheet
M&E | to 31st Dec | 3 | Hydrolysis HX Recirculation Pumps (M26) -Data Sheet | Y
M&E | to 31st Dec | 3 | Digester Feed Pumps (part of HPH Plant) (M13) -Data Sheet | Y
M&E | to 31st Dec | 3 | Pipework (M12) -Spec | Y
M&E | to 31st Dec | 3 | Mechanical Installation (M12) -Spec | Y
M&E | to 31st Dec | 3 | MCC inc ICA (E03) -Spec | Y
M&E | to 31st Dec | 3 | Steam Heating Units (Direct steam injection into sludge) (M35) -TAR
M&E | to 31st Dec | 3 | HPH Tanks V & PRV valves (M62) -TAR
M&E | to 31st Dec | 3 | Heat Exchanger Water Recirculation Pumps (M26) -TAR
M&E | to 31st Dec | 3 | Pasteurisation Tank Feed Pumps (M13) -TAR
M&E | to 31st Dec | 3 | Hydrolysis HX Recirculation Pumps (M26) -TAR
M&E | to 31st Dec | 3 | Digester Feed Pumps (part of HPH Plant) (M13) -TAR
M&E | to 31st Dec | 3 | Heat Exchanger Sludge Recirculation Pumps (M18) -TAR
M&E | to 31st Dec | 3 | 2nd Stage Heating Sludge Recirculation Pumps(also transfers sludge to Hydrolysis Tank) (M18) -TAR
M&E | to 31st Dec | 3 | Pasteurisation Tanks GA (M09) | Y
M&E | to 31st Dec | 3 | Hydrolysis Tank GA (M09) | Y
M&E | to 31st Dec | 3 | HPH Buffer Tank GA (Overflow tank) (M09) | Y
M&E | to 31st Dec | 3 | HPH GA | Y
M&E | to 31st Dec | 4 | MCC's FAT & SAT Test & Inspection Requirement | Y
M&E | to 31st Dec | 4 | Pipework (M12) -Spec | Y
M&E | to 31st Dec | 5 | Mechanical Installation (M12) -Spec | Y
M&E | to 31st Dec | 6 | Pressurisation unit (M27) -Data Sheet | Y
M&E | to 31st Dec | 6 | Hot water recirculation pumps - Motive Water system (M26) -Data Sheet | Y
M&E | to 31st Dec | 6 | Hot water recirculation pumps - CHP heat exchange (M26) -Data Sheet | Y
M&E | to 31st Dec | 6 | Pipework (M12) -Spec | Y
M&E | to 31st Dec | 6 | Mechanical Installation (M12) -Spec | Y
M&E | to 31st Dec | 6 | Structural steelwork and access plarforms (M20) -Spec
M&E | to 31st Dec | 6 | Steam system components inc condensate traps (M33) -Spec
M&E | to 31st Dec | 6 | Easiheat HX -TAR
M&E | to 31st Dec | 6 | Fuel oil Storage tank / Nat gas supply -TAR
M&E | to 31st Dec | 6 | Boiler water feed tank inc de-aerator and chemical dosing (M30 & M31) -TAR
M&E | to 31st Dec | 6 | Water Treatment Plant (Softening/Filtration/RO) (M28) -TAR
M&E | to 31st Dec | 6 | Hot water recirculation pumps - Motive Water system (M26) -TAR
M&E | to 31st Dec | 6 | Pressurisation unit (M27) -use existing -TAR | Y
M&E | to 31st Dec | 6 | Lifting equipment -Use existing -TAR | Y
M&E | to 31st Dec | 6 | Hot water recirculation pumps - CHP heat exchange (M26) -TAR
M&E | to 31st Dec | 6 | Composite Waste Heat Boilers (M03) -DRW
M&E | to 31st Dec | 6 | Water Treatment Plant (Softening/Filtration/RO) -DRW
M&E | to 31st Dec | 6 | Boiler water feed tank inc de-aerator and chemical dosing -DRW
M&E | to 31st Dec | 8 | Feeder Schedule | Y
M&E | to 31st Dec | 8 | I/O Schedule SCADA System | Y
M&E | to 31st Dec | 8 | DIGESTED SLUDGE BLOWERS (M60) -Data Sheet | Y
M&E | to 31st Dec | 8 | Centrifuge Feed Pumps (M13) -Data Sheet | Y
M&E | to 31st Dec | 8 | Leaf Spring DIFFUSERS (M61) -Data Sheet | Y
M&E | to 31st Dec | 8 | MCC inc ICA -Spec | Y
M&E | to 31st Dec | 8 | Pipework (M12) -Spec | Y
M&E | to 31st Dec | 8 | Mechanical Installation (M12) -Spec | Y
M&E | to 31st Dec | 8 | Fixed Inclined Conveyor (M06) -TAR
M&E | to 31st Dec | 8 | Bulk powder polyelectrolyte mechanical handling and storage system (M48) -TAR
M&E | to 31st Dec | 8 | Centrifuge Feed Pumps (M13) -TAR
M&E | to 31st Dec | 8 | DIGESTED SLUDGE BLOWERS (M60) -TAR
M&E | to 31st Dec | 8 | Dewatering Centrifuges (M04) -DRW
M&E | to 31st Dec | 9 | Liquor Treatment -TAR | Y
M&E | to 31st Dec | 10 | UPDWS - UV disinfection (M42)
M&E | to 31st Dec | 10 | Water booster package - duty/duty/standby pumps + accumulator -Data Sheet
M&E | to 31st Dec | 10 | Centrifugal Pumps (M18) -Data Sheet
M&E | to 31st Dec | 10 | FE/DW storage tank (M40) -Data Sheet
M&E | to 31st Dec | 10 | Water booster package - duty/duty/standby pumps + accumulator -Spec
M&E | to 31st Dec | 10 | Centrifugal Pumps (M18) -Spec
M&E | to 31st Dec | 10 | Self-cleaning Filters 300 micron (M39) -TAR
M&E | to 31st Dec | 10 | Self-cleaning Filters 100 micron (M39) -TAR
M&E | to 31st Dec | 10 | Centrifugal Pumps (M18) -TAR
M&E | to 31st Dec | 13 | Odour Treatment Plant #1 (M43) -TAR
Proc | to 31st Dec | 99 | Place Order on DEMA - M04
Proc | to 31st Dec |  | Place Order on DEMA - M06
Proc | to 31st Dec |  | Place Order on DEMA - M09 | Y
Proc | to 31st Dec |  | Place Order on DEMA - M10
Proc | to 31st Dec |  | Prepare Enquiry Package - M12
Proc | to 31st Dec |  | Prepare Enquiry Package - M13 | Y
Proc | to 31st Dec |  | Prepare Enquiry Package - M18
Proc | to 31st Dec |  | Prepare Enquiry Package - M20
Proc | to 31st Dec |  | Prepare Enquiry Package - M26 | Y
Proc | to 31st Dec |  | Prepare Enquiry Package - M33
Proc | to 31st Dec |  | Prepare Enquiry Package - M55
Proc | to 31st Dec |  | Prepare Enquiry Package - M60
Proc | to 31st Dec |  | Prepare Enquiry Package - E18
Proc | to 31st Dec |  | Place Order on DEMA - M05
Proc | to 31st Dec |  | Prepare Enquiry Package - M14
Proc | to 31st Dec |  | Place Order on DEMA - M11 | Y
Proc | to 31st Dec |  | Place Order on DEMA - M71
Proc | to 31st Dec |  | Place Order on DEMA - M24
Proc | to 31st Dec |  | Place Order on DEMA - M03
Proc | to 31st Dec |  | Place Order on DEMA - M25
Proc | to 31st Dec |  | Prepare Enquiry Package - M27 | Y
Proc | to 31st Dec |  | Prepare Enquiry Package - M28 | Y
Proc | to 31st Dec |  | Prepare Enquiry Package - M31 | Y
Proc | to 31st Dec |  | Prepare Enquiry Package - M65
Proc | to 31st Dec |  | Place Order on DEMA - M66 | Y
Proc | to 31st Dec |  | Prepare Enquiry Package - M56
Proc | to 31st Dec |  | Prepare Enquiry Package - M39
M&E | to 31st Dec | 11 | UPDWS - UV disinfection (M42) | Y
M&E | to 31st Dec | 11 | Pipeline UV System (M42) -Data Sheet | Y
M&E | to 31st Dec | 11 | Self-cleaning Filters 300 micron (M39) -Data Sheet | Y
M&E | to 31st Dec | 11 | Self-cleaning Filters 50 micron (M39) -Data Sheet | Y
M&E | to 31st Dec | 11 | Self-cleaning Filters 300 micron (M39) -Spec | Y
M&E | to 31st Dec | 11 | Self-cleaning Filters 50 micron (M39) -Spec | Y
M&E | to 31st Dec | 11 | Pipework (M12) -Spec | Y
M&E | to 31st Dec | 11 | Mechanical Installation (M12) -Spec | Y
Proc | to 31st Dec |  | Prepare Enquiry Package - M62 | Y
Civil | to 20th Jan | 0 | Vehicle tracking for all Road Layouts
Civil | to 20th Jan | 0 | Drainage -Main Spine
Civil | to 20th Jan | 0 | Drainage -HPH | Y
Civil | to 20th Jan | 8 | Cake Bund Layout GA Drawing (For Construction) | Y
Civil | to 20th Jan | 8 | Cake Bund Sections and Details Drawing inc RCD (For Construction) | Y
M&E | to 20th Jan | 0 | PFD related mass, heat and flows balance
M&E | to 20th Jan | 0 | Process Calculations
M&E | to 20th Jan | 0 | P&ID's
M&E | to 20th Jan | 0 | Process Description
M&E | to 20th Jan | 0 | Operating philosophy
M&E | to 20th Jan | 0 | BFD
M&E | to 20th Jan | 0 | SPEC - Electrical Installation - General
M&E | to 20th Jan | 0 | TAR - Electrical Installation - General
M&E | to 20th Jan | 0 | TAR - Mechanical Installation - General (M12)
M&E | to 20th Jan | 0 | HazOp Study
M&E | to 20th Jan | 1 | DS -SAS Sludge Screen (Strainpress) Feed Pumps (M18) | Y
M&E | to 20th Jan | 1 | DS -SAS Thickener Feed Pumps (M??) | Y
M&E | to 20th Jan | 1 | DS -Centrate Tank/Sump
M&E | to 20th Jan | 1 | DS -NEW SCOPE TBD: Blower @ Aeration Lane
M&E | to 20th Jan | 1 | SPEC -Electrical Installation
M&E | to 20th Jan | 1 | SPEC -Instrumentation - temperature | Y
M&E | to 20th Jan | 1 | SPEC -Tanker Import Logger (not in DMS) (M59)
M&E | to 20th Jan | 1 | SPEC -MCC kiosk
M&E | to 20th Jan | 1 | SPEC -NEW SCOPE TBD: Blower @ Aeration Lane
M&E | to 20th Jan | 1 | TAR -MCC inc ICA | Y
M&E | to 20th Jan | 1 | TAR -Liquid Polymer Make up system (M16) | Y
M&E | to 20th Jan | 1 | TAR -Instrumentation - temperature | Y
M&E | to 20th Jan | 1 | TAR -Polymer Dosing Pumps (M16) | Y
M&E | to 20th Jan | 1 | TAR -Mechanical Installation (M12)
M&E | to 20th Jan | 1 | TAR -Electrical Installation
M&E | to 20th Jan | 3 | DS -2nd Stage Heating Sludge Recirculation Pumps(also transfers sludge to Hydrolysis Tank) (M80) | Y
M&E | to 20th Jan | 3 | DS -Heat Exchanger Sludge Recirculation Pumps (M80) | Y
M&E | to 20th Jan | 3 | SPEC -Instrumentation - level | Y
M&E | to 20th Jan | 3 | SPEC -Instrumentation - flow | Y
M&E | to 20th Jan | 3 | SPEC -Instrumentation - pressure | Y
M&E | to 20th Jan | 3 | SPEC -Instrumentation - temperature | Y
M&E | to 20th Jan | 3 | SPEC -Electrical Installation | Y
M&E | to 20th Jan | 3 | SPEC -Structural steelwork and access plarforms (M20) | Y
M&E | to 20th Jan | 3 | TAR -Mechanical Installation (M12)
M&E | to 20th Jan | 3 | TAR -HPH Tanks V & PRV valves (M62)
M&E | to 20th Jan | 3 | TAR -Pasteurisation Tank Feed Pumps (M13)
M&E | to 20th Jan | 3 | TAR -Digester Feed Pumps (part of HPH Plant) (M13)
M&E | to 20th Jan | 3 | TAR -Instrumentation - flow
M&E | to 20th Jan | 3 | TAR -Instrumentation - pressure
M&E | to 20th Jan | 3 | TAR -Instrumentation - temperature
M&E | to 20th Jan | 3 | TAR -Heat Exchanger Water Recirculation Pumps (M26)
M&E | to 20th Jan | 3 | TAR -Hydrolysis HX Recirculation Pumps (M26)
M&E | to 20th Jan | 3 | TAR -MCC inc ICA
M&E | to 20th Jan | 3 | TAR -Electrical Installation
M&E | to 20th Jan | 4 | TAR -Instrumentation - flow
M&E | to 20th Jan | 4 | TAR -Instrumentation - pressure
M&E | to 20th Jan | 4 | TAR -Instrumentation - temperature
M&E | to 20th Jan | 5 | SPEC -Electrical Installation | Y
M&E | to 20th Jan | 5 | TAR -Electrical Installation
M&E | to 20th Jan | 5 | TAR -Mechanical Installation (M12)
M&E | to 20th Jan | 6 | SPEC -Electrical Installation
M&E | to 20th Jan | 6 | SPEC -Structural steelwork and access plarforms (M20) | Y
M&E | to 20th Jan | 6 | SPEC -Mechanical Installation (M12)
M&E | to 20th Jan | 6 | SPEC -Gas Detection (E23)
M&E | to 20th Jan | 6 | TAR -Easiheat HX | Y
M&E | to 20th Jan | 6 | TAR -Fuel oil Storage tank / Nat gas supply
M&E | to 20th Jan | 6 | TAR -MCC inc ICA
M&E | to 20th Jan | 6 | TAR -Mechanical Installation (M12)
M&E | to 20th Jan | 6 | TAR -Hot water recirculation pumps - Motive Water system (M26)
M&E | to 20th Jan | 6 | TAR -Hot water recirculation pumps - CHP heat exchange (M26)
M&E | to 20th Jan | 6 | TAR -Instrumentation - flow
M&E | to 20th Jan | 6 | TAR -Instrumentation - pressure
M&E | to 20th Jan | 6 | TAR -Instrumentation - temperature
M&E | to 20th Jan | 6 | TAR -Gas Detection (E23)
M&E | to 20th Jan | 6 | TAR -Electrical Installation
M&E | to 20th Jan | 8 | P&IDs
M&E | to 20th Jan | 8 | SPEC -Electrical Installation
M&E | to 20th Jan | 8 | SPEC -Mechanical Installation (M12)
M&E | to 20th Jan | 8 | SPEC -Structural steelwork and access plarforms (M20)
M&E | to 20th Jan | 8 | TAR -Fixed Inclined Conveyor (M06) | Y
M&E | to 20th Jan | 8 | TAR -Bulk powder polyelectrolyte mechanical handling and storage system (M48) | Y
M&E | to 20th Jan | 8 | TAR -Centrifuge Feed Pumps (M13)
M&E | to 20th Jan | 8 | TAR -MCC inc ICA
M&E | to 20th Jan | 8 | TAR -Instrumentation - flow
M&E | to 20th Jan | 8 | TAR -Instrumentation - pressure
M&E | to 20th Jan | 8 | TAR -Instrumentation - temperature
M&E | to 20th Jan | 8 | TAR -Electrical Installation
M&E | to 20th Jan | 8 | TAR -Leaf Spring DIFFUSERS (M12)
M&E | to 20th Jan | 9 | TAR -Safety Shower with Heated Header Tank (M38) | Y
M&E | to 20th Jan | 10 | DS -SILOXANE REMOVAL PACKAGE PLANT (M56)
M&E | to 20th Jan | 10 | SPEC -SILOXANE REMOVAL PACKAGE PLANT (M56)
M&E | to 20th Jan | 11 | DS -Water booster package - duty/duty/standby pumps + accumulator
M&E | to 20th Jan | 11 | DS -Centrifugal Pumps (M18) | Y
M&E | to 20th Jan | 11 | SPEC -Water booster package - duty/duty/standby pumps + accumulator
M&E | to 20th Jan | 11 | SPEC -Pipeline UV System (M42)
M&E | to 20th Jan | 11 | SPEC -Mechanical Installation (M12)
M&E | to 20th Jan | 11 | SPEC -Centrifugal Pumps (M18) | Y
M&E | to 20th Jan | 11 | SPEC -Structural steelwork and access plarforms (M20)
M&E | to 20th Jan | 11 | SPEC -Electrical Installation
M&E | to 20th Jan | 11 | TAR -Self-cleaning Filters 300 micron (M39)
M&E | to 20th Jan | 11 | TAR -Self-cleaning Filters 100 micron (M39)
M&E | to 20th Jan | 11 | TAR -Instrumentation - flow
M&E | to 20th Jan | 11 | TAR -Instrumentation - pressure
M&E | to 20th Jan | 11 | TAR -Instrumentation - temperature
M&E | to 20th Jan | 11 | TAR -Mechanical Installation (M12)
M&E | to 20th Jan | 13 | P&ID's
M&E | to 20th Jan | 13 | TAR -Odour Treatment Plant #1 (M43)
M&E | to 20th Jan | 13 | TAR -Odour ductwork (M43)
M&E | to 20th Jan | 13 | TAR -Odour Treatment Plant #2 (M43)
M&E | to 20th Jan | 13 | TAR -Odour ductwork (M43)
Proc | to 20th Jan |  | Place Order on DEMA - M04
Proc | to 20th Jan |  | Place Order on DEMA - M10
Proc | to 20th Jan |  | Prepare Enquiry Package - M12
Proc | to 20th Jan |  | Prepare Enquiry Package - M20
Proc | to 20th Jan |  | Prepare Enquiry Package - M60 | Y
Proc | to 20th Jan |  | Place Order on DEMA - M05 | Y
Proc | to 20th Jan |  | Prepare Enquiry Package - Blower @ Aeration laneTBD
Proc | to 20th Jan |  | Place Order on DEMA - M24
Proc | to 20th Jan |  | Place Order on DEMA - M03 | Y
Proc | to 20th Jan |  | Place Order on DEMA - M25 | Y
Proc | to 20th Jan |  | Prepare Enquiry Package - M61 | Y
Proc | to 20th Jan |  | Place Order on DEMA - M66
Proc | to 20th Jan |  | Prepare Enquiry Package - M56
Proc | to 20th Jan |  | Prepare Enquiry Package - M39 | Y
Proc | to 20th Jan |  | Prepare Enquiry Package - M42 | Y
Civil | to 24th Feb | 99 | Vehicle tracking for all Road Layouts | Y
Civil | to 24th Feb | 99 | Drainage -Main Spine | Y
Civil | to 24th Feb | 99 | GA & RCD Drawing (for Construction) -PIPE BRIDGE | y
Civil | to 24th Feb | 1 | GA Drawing (for Construction) -Thckening Centrifuges
Civil | to 24th Feb | 1 | RCD Drawing -Thickening Centrifuges
Civil | to 24th Feb | 1 | RCD Drawing -Poly Silo Bund
Civil | to 24th Feb | 1 | GA & RCD Drawing (for Construction) -Thickening feed pump | Y
Civil | to 24th Feb | 6 | GA & Piling Drawing (Construction) -Flue Stack
Civil | to 24th Feb | 6 | RCD Drawing -Flue Stack
Civil | to 24th Feb | 6 | GA Drawing (Construction) -Boiler
Civil | to 24th Feb | 6 | GA Drawing (Construction) -Wall Mods
Civil | to 24th Feb | 8 | GA & RCD Drawing (for Construction) -Dewatering feed pumps | Y
Civil | to 24th Feb | 8 | GA & RCD Drawing (for Construction) -Dewatering forwarding pumps | y
M&E | to 24th Feb | 99 | P&ID's
M&E | to 24th Feb | 99 | Operating philosophy
M&E | to 24th Feb | 99 | PFD related mass, heat and flows balance
M&E | to 24th Feb | 99 | Process Calculations
M&E | to 24th Feb | 99 | Process Description
M&E | to 24th Feb | 99 | Spec -Electrical Installation - General | y
M&E | to 24th Feb | 99 | Spec -Valves - General (M44)
M&E | to 24th Feb | 99 | TAR -Electrical Installation - General
M&E | to 24th Feb | 99 | TAR -MCC's / ICA's | y
M&E | to 24th Feb | 99 | TAR -Mechanical Installation - General (M12)
M&E | to 24th Feb | 99 | TAR -Valves - General (M44)
M&E | to 24th Feb | 99 | HazOp Study -
M&E | to 24th Feb | 99 | HazOp Study -Steam
M&E | to 24th Feb | 1 | DS -Centrate Pumps - return of centrate to WwTW (M18) | y
M&E | to 24th Feb | 1 | Spec -Electrical Installation | y
M&E | to 24th Feb | 1 | Spec -Instrumentation - level | y
M&E | to 24th Feb | 1 | spec -Instrumentation - flow | y
M&E | to 24th Feb | 1 | spec -Instrumentation - pressure | y
M&E | to 24th Feb | 1 | spec -Valves (M44)
M&E | to 24th Feb | 1 | spec -Tanker Import Logger (not in DMS) (M59) | y
M&E | to 24th Feb | 1 | spec -MCC kiosk | y
M&E | to 24th Feb | 1 | tar -Instrumentation - level | y
M&E | to 24th Feb | 1 | tar -Instrumentation - flow | y
M&E | to 24th Feb | 1 | tar -Instrumentation - pressure | y
M&E | to 24th Feb | 1 | tar -Instrumentation - temperature | y
M&E | to 24th Feb | 1 | tar -Pipework (M12)
M&E | to 24th Feb | 1 | tar -Valves (M44)
M&E | to 24th Feb | 1 | tar -Mechanical Installation (M12)
M&E | to 24th Feb | 1 | tar -Electrical Installation
M&E | to 24th Feb | 1 | tar -Centrate Pumps - return of centrate to WwTW (M18) | y
M&E | to 24th Feb | 3 | P&ID's
M&E | to 24th Feb | 3 | Control Philosophy
M&E | to 24th Feb | 3 | spec -Pipework (M12) | y
M&E | to 24th Feb | 3 | spec -Valves (M44)
M&E | to 24th Feb | 3 | spec -Structural steelwork and access plarforms (M20) | y
M&E | to 24th Feb | 3 | spec -Lightning protection installation
M&E | to 24th Feb | 3 | tar -Steam Heating Units (Direct steam injection into sludge) (M35) | y
M&E | to 24th Feb | 3 | tar -Pipework (M12)
M&E | to 24th Feb | 3 | tar -Valves (M44)
M&E | to 24th Feb | 3 | tar -Mechanical Installation (M12)
M&E | to 24th Feb | 3 | tar -Pasteurisation Tank Feed Pumps (M13) | y
M&E | to 24th Feb | 3 | tar -Digester Feed Pumps (part of HPH Plant) (M13) | y
M&E | to 24th Feb | 3 | tar -Heat Exchanger Water Recirculation Pumps (M26) | y
M&E | to 24th Feb | 3 | tar -Hydrolysis HX Recirculation Pumps (M26) | y
M&E | to 24th Feb | 3 | tar -MCC inc ICA | y
M&E | to 24th Feb | 3 | tar -Heat Exchanger Sludge Recirculation Pumps (M80) | y
M&E | to 24th Feb | 3 | tar -2nd Stage Heating Sludge Recirculation Pumps(also transfers sludge to Hydrolysis Tank) (M80) | y
M&E | to 24th Feb | 3 | tar -Electrical Installation
M&E | to 24th Feb | 3 | tar -Structural steelwork and access plarforms (M20)
M&E | to 24th Feb | 4 | P&ID's
M&E | to 24th Feb | 4 | spec -Valves (M44) | y
M&E | to 24th Feb | 4 | spec -Pipework (M12) | y
M&E | to 24th Feb | 4 | spec -Lightning protection installation
M&E | to 24th Feb | 4 | tar -Valves (M44)
M&E | to 24th Feb | 4 | tar -Structural steelwork and access plarforms (M20)
M&E | to 24th Feb | 5 | tar -Electrical Installation
M&E | to 24th Feb | 5 | tar -Mechanical Installation (M12)
M&E | to 24th Feb | 6 | P&ID's
M&E | to 24th Feb | 6 | spec -Electrical Installation | y
M&E | to 24th Feb | 6 | spec -Structural steelwork and access plarforms (M20) | y
M&E | to 24th Feb | 6 | spec -Steam system components inc condensate traps (M33) | y
M&E | to 24th Feb | 6 | spec -Pipework (M12) | y
M&E | to 24th Feb | 6 | spec -Valves (M44) | y
M&E | to 24th Feb | 6 | spec -Mechanical Installation (M12) | y
M&E | to 24th Feb | 6 | spec -Gas Detection (E23)
M&E | to 24th Feb | 6 | spec -Building Services and Lighting
M&E | to 24th Feb | 6 | spec -Lightning protection installation |  | ?
M&E | to 24th Feb | 6 | tar -Fuel oil Storage tank / Nat gas supply | y
M&E | to 24th Feb | 6 | tar -MCC inc ICA | y
M&E | to 24th Feb | 6 | tar -Hot water recirculation pumps - Motive Water system (M26) | y
M&E | to 24th Feb | 6 | tar -Hot water recirculation pumps - CHP heat exchange (M26) | y
M&E | to 24th Feb | 6 | tar -Boiler water feed tank inc de-aerator and chemical dosing (M30 & M31) | y
M&E | to 24th Feb | 6 | tar -Pipework
M&E | to 24th Feb | 6 | tar -Valves (M44)
M&E | to 24th Feb | 6 | tar -Mechanical Installation (M12)
M&E | to 24th Feb | 6 | tar -Electrical Installation
M&E | to 24th Feb | 6 | tar -Gas Detection (E23)
M&E | to 24th Feb | 6 | tar -Structural steelwork and access plarforms (M20)
M&E | to 24th Feb | 6 | tar -Building Ventilation (M45)
M&E | to 24th Feb | 6 | tar -Steam system components inc. condensate traps (M33)
M&E | to 24th Feb | 6 | tar -Building Services and Lighting
M&E | to 24th Feb | 8 | P&IDs
M&E | to 24th Feb | 8 | spec -Electrical Installation | y
M&E | to 24th Feb | 8 | spec -Mechanical Installation (M12) | y
M&E | to 24th Feb | 8 | spec -Pipework (M12)
M&E | to 24th Feb | 8 | spec -Valves (M44)
M&E | to 24th Feb | 8 | spec -Structural steelwork and access plarforms (M20) | y
M&E | to 24th Feb | 8 | spec -Lightning protection installation
M&E | to 24th Feb | 8 | tar -Centrifuge Feed Pumps (M13) | y
M&E | to 24th Feb | 8 | tar -MCC inc ICA | y
M&E | to 24th Feb | 8 | tar -Mechanical Installation (M12)
M&E | to 24th Feb | 8 | tar -Electrical Installation
M&E | to 24th Feb | 8 | tar -Leaf Spring DIFFUSERS (M61) | y
M&E | to 24th Feb | 8 | tar -Pipework (M12)
M&E | to 24th Feb | 8 | tar -Structural steelwork and access plarforms (M20)
M&E | to 24th Feb | 8 | tar -Valves (M44)
M&E | to 24th Feb | 10 | tar -SILOXANE REMOVAL PACKAGE PLANT (M56)
M&E | to 24th Feb | 11 | PFD related mass, heat and flows balance
M&E | to 24th Feb | 11 | UPDWS - UV disinfection (M42) | y
M&E | to 24th Feb | 11 | P&ID's
M&E | to 24th Feb | 11 | DS -Water booster package - duty/duty/standby pumps + accumulator
M&E | to 24th Feb | 11 | spec -Water booster package - duty/duty/standby pumps + accumulator
M&E | to 24th Feb | 11 | spec -Pipeline UV System (M42) | y
M&E | to 24th Feb | 11 | spec -Pipework (M12) | y
M&E | to 24th Feb | 11 | spec -Valves (M44)
M&E | to 24th Feb | 11 | spec -Mechanical Installation (M12) | y
M&E | to 24th Feb | 11 | spec -Structural steelwork and access plarforms (M20) | y
M&E | to 24th Feb | 11 | spec -Electrical Installation
M&E | to 24th Feb | 11 | spec -Instrumentation - level
M&E | to 24th Feb | 11 | spec -Instrumentation - flow
M&E | to 24th Feb | 11 | spec -Instrumentation - pressure
M&E | to 24th Feb | 11 | spec -Instrumentation - temperature
M&E | to 24th Feb | 11 | spec -Lightning protection installation
M&E | to 24th Feb | 11 | tar -Self-cleaning Filters 300 micron (M39)
M&E | to 24th Feb | 11 | tar -Self-cleaning Filters 100 micron (M39)
M&E | to 24th Feb | 11 | tar -Instrumentation - flow
M&E | to 24th Feb | 11 | tar -Instrumentation - pressure
M&E | to 24th Feb | 11 | tar -Instrumentation - temperature
M&E | to 24th Feb | 11 | tar -Pipework (M12)
M&E | to 24th Feb | 11 | tar -Mechanical Installation (M12)
M&E | to 24th Feb | 11 | tar -Electrical Installation
M&E | to 24th Feb | 11 | tar -Structural steelwork and access plarforms (M20)
M&E | to 24th Feb | 11 | tar -Valves (M44)
M&E | to 24th Feb | 11 | tar -Centrifugal Pumps (M18) | y
M&E | to 24th Feb | 13 | tar -Odour Treatment Plant #1 (M43) | y
M&E | to 24th Feb | 13 | tar -Odour ductwork (M43) | y
M&E | to 24th Feb | 13 | tar -Odour Treatment Plant #2 (M43) | y
M&E | to 24th Feb | 13 | tar -Odour ductwork (M43) | y
Proc | to 24th Feb | 99 | Place Order on DEMA - M04 | y
Proc | to 24th Feb | 99 | Place Order on DEMA - M06 | y
Proc | to 24th Feb | 99 | Place Order on DEMA - M10 | y
Proc | to 24th Feb | 99 | Prepare Enquiry Package - M12 | y
Proc | to 24th Feb | 99 | Tender Duration - M12 | y
Proc | to 24th Feb | 99 | Place Order on DEMA - M13
Proc | to 24th Feb | 99 | Prepare Enquiry Package - M18 | y
Proc | to 24th Feb | 99 | Tender Duration - M18 | y
Proc | to 24th Feb | 99 | Place Order on DEMA - M18
Proc | to 24th Feb | 99 | Prepare Enquiry Package - M20 | y
Proc | to 24th Feb | 99 | Tender Duration - M20 | y
Proc | to 24th Feb | 99 | Tender Duration - M26 | y
Proc | to 24th Feb | 99 | Place Order on DEMA - M26
Proc | to 24th Feb | 99 | Prepare Enquiry Package - M33 | y
Proc | to 24th Feb | 99 | Tender Duration - M33
Proc | to 24th Feb | 99 | Prepare Enquiry Package - M44
Proc | to 24th Feb | 99 | Tender Duration - M44
Proc | to 24th Feb | 99 | Place Order on DEMA - M44
Proc | to 24th Feb | 99 | Place Order on DEMA - M45
Proc | to 24th Feb | 99 | Place Order on DEMA - M60
Proc | to 24th Feb | 99 | Place Order on DEMA - M62
Proc | to 24th Feb | 99 | Tender Duration - E02
Proc | to 24th Feb | 99 | Prepare Enquiry Package - E18
Proc | to 24th Feb | 99 | Prepare Enquiry Package - E24
Proc | to 24th Feb | 99 | Tender Duration - E24
Proc | to 24th Feb | 99 | Prepare Enquiry Package - E26
Proc | to 24th Feb | 1 | Place Order on DEMA - M14
Proc | to 24th Feb | 1 | Place Order on DEMA - M16 | y
Proc | to 24th Feb | 1 | Prepare Enquiry Package - M59 | y
Proc | to 24th Feb | 1 | Tender Duration - M59
Proc | to 24th Feb | 3 | Place Order on DEMA - M35
Proc | to 24th Feb | 3 | Prepare Enquiry Package - M49 | y
Proc | to 24th Feb | 3 | Tender Duration - M49 | y
Proc | to 24th Feb | 3 | Place Order on DEMA - M71
Proc | to 24th Feb | 3 | Tender Duration - M80 | y
Proc | to 24th Feb | 3 | Place Order on DEMA - M80
Proc | to 24th Feb | 5 | Place Order on DEMA - M24 | y
Proc | to 24th Feb | 6 | Place Order on DEMA - M28 | y
Proc | to 24th Feb | 6 | Place Order on DEMA - M30
Proc | to 24th Feb | 6 | Tender Duration - M31 | y
Proc | to 24th Feb | 7 | Place Order on DEMA - E03 | y
Proc | to 24th Feb | 7 | Prepare Enquiry Package - E06 | y
Proc | to 24th Feb | 7 | Tender Duration - E06 | y
Proc | to 24th Feb | 8 | Place Order on DEMA - M48 | y
Proc | to 24th Feb | 8 | Place Order on DEMA - M61 | y
Proc | to 24th Feb | 9 | Place Order on DEMA - M66 | y
Proc | to 24th Feb | 10 | Prepare Enquiry Package - M56
Proc | to 24th Feb | 10 | Tender Duration - M56
Proc | to 24th Feb | 10 | Place Order on DEMA - M56
Proc | to 24th Feb | 11 | Place Order on DEMA - M39
Proc | to 24th Feb | 13 | Tender Duration - M43 | y
Proc | to 24th Feb | 13 | Place Order on DEMA - M43
Civil | to 23rd Mar | 3 | HPH MCC Kiosk
Civil | to 23rd Mar | 5 | WGB
Civil | to 23rd Mar | 6 | Flue Base | Y
Civil | to 23rd Mar | 1 | Centrifuge Feed pump slab | Y
Civil | to 23rd Mar | 6 | Boiler slab | Y
Civil | to 23rd Mar | 8 | Poly bund
Civil | to 23rd Mar | 8 | Post-Dig mods
Civil | to 23rd Mar | 9 | LTP Setting out | Y
Civil | to 23rd Mar | 13 | SHT OCU base | Y
M&E | to 23rd Mar | 99 | Operating philosophy
M&E | to 23rd Mar | 99 | Control Philosophy
M&E | to 23rd Mar | 99 | spec -Mechanical Installation (M12) | Y
M&E | to 23rd Mar | 99 | SPEC - Electrical Installation - General | y
M&E | to 23rd Mar | 99 | spec - instruments
M&E | to 23rd Mar | 99 | spec - valves
M&E | to 23rd Mar | 99 | TAR - Electrical Installation - General
M&E | to 23rd Mar | 99 | tar - MCCs | Y
M&E | to 23rd Mar | 99 | tar - instruments
M&E | to 23rd Mar | 99 | TAR - Mechanical Installation - General (M12) | Y
M&E | to 23rd Mar | 99 | tar - valves
M&E | to 23rd Mar | 1 | ds - PST Autodesludging
M&E | to 23rd Mar | 1 | ds - Centrate Tank/Sump | Y
M&E | to 23rd Mar | 1 | spec - electrical Installation | y
M&E | to 23rd Mar | 1 | spec - mech install | y
M&E | to 23rd Mar | 1 | spec - valves | y
M&E | to 23rd Mar | 1 | spec - pipework | y
M&E | to 23rd Mar | 1 | spec- tanker import logger | y
M&E | to 23rd Mar | 1 | tar - pipework | y
M&E | to 23rd Mar | 1 | tar - valves
M&E | to 23rd Mar | 1 | tar - mechanical Installation | y
M&E | to 23rd Mar | 1 | tar - electrical Installation
M&E | to 23rd Mar | 1 | tar - Centrate Pumps - return of centrate to WwTW (M18) | y
M&E | to 23rd Mar | 1 | tar - MCC kiosk | y
M&E | to 23rd Mar | 3 | spec - valves | y
M&E | to 23rd Mar | 3 | spec - pipework | y
M&E | to 23rd Mar | 3 | spec- lightning protection
M&E | to 23rd Mar | 3 | tar - pipework | y
M&E | to 23rd Mar | 3 | tar - valves
M&E | to 23rd Mar | 3 | tar - mechanical Installation | y
M&E | to 23rd Mar | 3 | tar - HPH Tanks V & PRV valves (M62)
M&E | to 23rd Mar | 3 | tar - Instrumentation - level
M&E | to 23rd Mar | 3 | tar - Instrumentation - flow
M&E | to 23rd Mar | 3 | tar - Instrumentation - pressure
M&E | to 23rd Mar | 3 | tar - Instrumentation - temperature
M&E | to 23rd Mar | 3 | tar - Heat Exchanger Water Recirculation Pumps (M26) | y
M&E | to 23rd Mar | 3 | tar - Hydrolysis HX Recirculation Pumps (M26) | y
M&E | to 23rd Mar | 3 | tar -Electrical Installation
M&E | to 23rd Mar | 3 | tar -Structural steelwork and access plarforms (M20)
M&E | to 23rd Mar | 4 | spec- lightning protection
M&E | to 23rd Mar | 4 | tar - Instrumentation - level
M&E | to 23rd Mar | 4 | tar - Instrumentation - flow
M&E | to 23rd Mar | 4 | tar - Instrumentation - pressure
M&E | to 23rd Mar | 4 | tar - Instrumentation - temperature
M&E | to 23rd Mar | 4 | tar -Structural steelwork and access plarforms (M20)
M&E | to 23rd Mar | 4 | tar - valves
M&E | to 23rd Mar | 5 | tar -Electrical Installation
M&E | to 23rd Mar | 5 | tar - mechanical Installation
M&E | to 23rd Mar | 6 | spec - valves | y
M&E | to 23rd Mar | 6 | spec -Building Services and Lighting
M&E | to 23rd Mar | 6 | spec -Gas Detection (E23)
M&E | to 23rd Mar | 6 | spec- lightning protection
M&E | to 23rd Mar | 6 | tar - Hot water recirculation pumps - Motive Water system (M26) | y
M&E | to 23rd Mar | 6 | tar - Hot water recirculation pumps - CHP heat exchange (M26) | y
M&E | to 23rd Mar | 6 | tar - Instrumentation - level
M&E | to 23rd Mar | 6 | tar - Instrumentation - flow
M&E | to 23rd Mar | 6 | tar - Instrumentation - pressure
M&E | to 23rd Mar | 6 | tar - Instrumentation - temperature
M&E | to 23rd Mar | 6 | tar - mechanical Installation | y
M&E | to 23rd Mar | 6 | tar - pipework | y
M&E | to 23rd Mar | 6 | tar - valves
M&E | to 23rd Mar | 6 | tar - Steam system components inc. condensate traps (M33)
M&E | to 23rd Mar | 6 | tar - Electrical Installation
M&E | to 23rd Mar | 6 | tar - Gas Detection (E23)
M&E | to 23rd Mar | 6 | tar - Structural steelwork and access plarforms (M20)
M&E | to 23rd Mar | 6 | tar - Building Ventilation (M45)
M&E | to 23rd Mar | 6 | tar - Building Services and Lighting
M&E | to 23rd Mar | 8 | spec - Electrical Installation | y
M&E | to 23rd Mar | 8 | spec - Mechanical Installation (M12) | y
M&E | to 23rd Mar | 8 | spec - Pipework (M12) | y
M&E | to 23rd Mar | 8 | spec -Valves (M44)
M&E | to 23rd Mar | 8 | spec -Building Services and Lighting
M&E | to 23rd Mar | 8 | spec -Lightning protection installation
M&E | to 23rd Mar | 8 | tar - Mechanical Installation (M12) | y
M&E | to 23rd Mar | 8 | tar 0- DIGESTED SLUDGE BLOWERS (M60) | y
M&E | to 23rd Mar | 8 | tar - Instrumentation - level
M&E | to 23rd Mar | 8 | tar - Instrumentation - flow
M&E | to 23rd Mar | 8 | tar - Instrumentation - pressure
M&E | to 23rd Mar | 8 | tar - Instrumentation - temperature
M&E | to 23rd Mar | 8 | tar 0- Electrical Installation
M&E | to 23rd Mar | 8 | tar - Leaf Spring DIFFUSERS (M61) | y
M&E | to 23rd Mar | 8 | tar - Pipework (M12) | y
M&E | to 23rd Mar | 8 | tar - Structural steelwork and access plarforms (M20)
M&E | to 23rd Mar | 8 | tar - Valves (M44)
M&E | to 23rd Mar | 8 | tar - Building Services and Lighting
M&E | to 23rd Mar | 10 | ds - SILOXANE REMOVAL PACKAGE PLANT (M56) | y
M&E | to 23rd Mar | 10 | spec - SILOXANE REMOVAL PACKAGE PLANT (M56) | y
M&E | to 23rd Mar | 10 | tar 0- SILOXANE REMOVAL PACKAGE PLANT (M56)
M&E | to 23rd Mar | 11 | ds - Water booster package - duty/duty/standby pumps + accumulator | y
M&E | to 23rd Mar | 11 | ds - FE/DW storage tank (M40) | y
M&E | to 23rd Mar | 11 | spec - Water booster package - duty/duty/standby pumps + accumulator | y
M&E | to 23rd Mar | 11 | spec - Valves (M44)
M&E | to 23rd Mar | 11 | spec - Mechanical Installation (M12) | y
M&E | to 23rd Mar | 11 | spec - Electrical Installation | y
M&E | to 23rd Mar | 11 | spec - Instrumentation - level | y
M&E | to 23rd Mar | 11 | spec - Instrumentation - flow | y
M&E | to 23rd Mar | 11 | spec - Instrumentation - pressure | y
M&E | to 23rd Mar | 11 | spec - FE/DW storage tank (M40) | y
M&E | to 23rd Mar | 11 | spec - Lightning protection installation
M&E | to 23rd Mar | 11 | tar - Centrifugal Pumps (M18) | y
M&E | to 23rd Mar | 11 | tar - Self-cleaning Filters 300 micron (M39) | y
M&E | to 23rd Mar | 11 | tar - Self-cleaning Filters 100 micron (M39) | y
M&E | to 23rd Mar | 11 | tar - Pipework (M12) | y
M&E | to 23rd Mar | 11 | tar - Structural steelwork and access plarforms (M20) | y
M&E | to 23rd Mar | 11 | tar - Instrumentation - level
M&E | to 23rd Mar | 11 | tar - Instrumentation - flow
M&E | to 23rd Mar | 11 | tar - Instrumentation - pressure
M&E | to 23rd Mar | 11 | tar - Instrumentation - temperature
M&E | to 23rd Mar | 11 | tar - Mechanical Installation (M12)
M&E | to 23rd Mar | 11 | tar - Electrical Installation
M&E | to 23rd Mar | 11 | tar - FE/DW storage tank (M40)
M&E | to 23rd Mar | 11 | tar - Valves (M44)
M&E | to 23rd Mar | 13 | tar - Odour Treatment Plant #1 (M43) | y
M&E | to 23rd Mar | 13 | tar - Odour Treatment Plant #2 (M43) | y
M&E | to 23rd Mar | 13 | tar - Odour ductwork (M43) | y
M&E | to 23rd Mar | 13 | tar - Odour ductwork (M43) | y
proc | to 23rd Mar |  | Place Order on DEMA - M04 | y
proc | to 23rd Mar |  | Place Order on DEMA - M06 | y
proc | to 23rd Mar |  | Earliest Delivery Date - M09 | y
proc | to 23rd Mar |  | Place Order on DEMA - M12
proc | to 23rd Mar |  | Prepare Enquiry Package - M12B | y
proc | to 23rd Mar |  | Place Order on DEMA - M13
proc | to 23rd Mar |  | Place Order on DEMA - M20
proc | to 23rd Mar |  | Place Order on DEMA - M26
proc | to 23rd Mar |  | Prepare Enquiry Package - M33 | y
proc | to 23rd Mar |  | Place Order on DEMA - M33
proc | to 23rd Mar |  | Prepare Enquiry Package - M40 | y
proc | to 23rd Mar |  | Prepare Enquiry Package - M44
proc | to 23rd Mar |  | Place Order on DEMA - M45
proc | to 23rd Mar |  | Place Order on DEMA - M60
proc | to 23rd Mar |  | Place Order on DEMA - M62
proc | to 23rd Mar |  | Place Order on DEMA - M14
proc | to 23rd Mar |  | Place Order on DEMA - M16 | y
proc | to 23rd Mar |  | Prepare Enquiry Package - M59 | y
proc | to 23rd Mar |  | Prepare Enquiry Package - New aeration blower | y
proc | to 23rd Mar |  | Earliest Delivery Date - M11
proc | to 23rd Mar |  | Place Order on DEMA - M35 | y
proc | to 23rd Mar |  | Place Order on DEMA - M71
proc | to 23rd Mar |  | Place Order on DEMA - M80 | y
proc | to 23rd Mar |  | Place Order on DEMA - M28 | y
proc | to 23rd Mar |  | Place Order on DEMA - M29 | y
proc | to 23rd Mar |  | Place Order on DEMA - M30 | y
proc | to 23rd Mar |  | Place Order on DEMA - M31
proc | to 23rd Mar |  | Place Order on DEMA - E03 | y
proc | to 23rd Mar |  | Place Order on DEMA - E06
proc | to 23rd Mar |  | Place Order on DEMA - M48 | y
proc | to 23rd Mar |  | Place Order on DEMA - M61 | y
proc | to 23rd Mar |  | Earliest Delivery Date - M61 | y
proc | to 23rd Mar |  | Prepare Enquiry Package - M56 | y
proc | to 23rd Mar |  | Place Order on DEMA - M56
proc | to 23rd Mar |  | Place Order on DEMA - M39
proc | to 23rd Mar |  | Place Order on DEMA - M43
Civil | to 20th Apr | 1 | Thickening Centrifuges (M04)
Civil | to 20th Apr | 1 | Poly bund
Civil | to 20th Apr | 3 | MCC base
Civil | to 20th Apr | 5 | WGB slab | Y
Civil | to 20th Apr | 6 | Boiler slab | Y
Civil | to 20th Apr | 8 | Centrifuge slab | Y
Civil | to 20th Apr | 8 | Poly bund | Y
Civil | to 20th Apr | 8 | MCC base
Civil | to 20th Apr | 8 | Post-Dig mods
Civil | to 20th Apr | 9 | Blowers slab
Civil | to 20th Apr | 9 | Glycerol / Caustic base
M&E | to 20th Apr | 99 | TAR -instruments
M&E | to 20th Apr | 99 | TAR -E15 | Y
M&E | to 20th Apr | 99 | TAR -valves
M&E | to 20th Apr | 1 | SPEC -Local area lighting | Y
M&E | to 20th Apr | 1 | TAR - Centrate Tank/Sump | Y
M&E | to 20th Apr | 1 | TAR -E02 | Y
M&E | to 20th Apr | 1 | TAR -M59 | Y
M&E | to 20th Apr | 3 | TAR -M44 | Y
M&E | to 20th Apr | 3 | TAR - M62 | Y
M&E | to 20th Apr | 3 | TAR -E13 | Y
M&E | to 20th Apr | 3 | TAR -E20 | Y
M&E | to 20th Apr | 3 | TAR -E21 | Y
M&E | to 20th Apr | 3 | TAR -E02 | Y
M&E | to 20th Apr | 3 | TAR -M20 | Y
M&E | to 20th Apr | 3 | TAR -E19 | Y
M&E | to 20th Apr | 4 | Spec - M44 | Y
M&E | to 20th Apr | 4 | TAR -M44 | Y
M&E | to 20th Apr | 4 | TAR -M20 | Y
M&E | to 20th Apr | 4 | TAR -E19 | Y
M&E | to 20th Apr | 5 | Detailed Design handover package to site team | Y
M&E | to 20th Apr | 5 | Detailed Design handover package to commissioning team | Y
M&E | to 20th Apr | 5 | TAR -E02 | Y
M&E | to 20th Apr | 5 | TAR -M12 | Y
M&E | to 20th Apr | 6 | SPEC -Lightning protection installation
M&E | to 20th Apr | 6 | Spec - Building services | Y
M&E | to 20th Apr | 6 | TAR -E19 | Y
M&E | to 20th Apr | 6 | TAR -E02 | Y
M&E | to 20th Apr | 6 | TAR -M20 | Y
M&E | to 20th Apr | 6 | TAR -M33 | Y
M&E | to 20th Apr | 6 | TAR -M44 | Y
M&E | to 20th Apr | 6 | TAR -E23 | Y
M&E | to 20th Apr | 6 | TAR -Building Services and Lighting | Y
M&E | to 20th Apr | 8 | spec - Lightning protection installation
M&E | to 20th Apr | 8 | Spec - Building services | Y
M&E | to 20th Apr | 8 | Spec -M44 | Y
M&E | to 20th Apr | 8 | TAR -E19 | Y
M&E | to 20th Apr | 8 | TAR -VALVES
M&E | to 20th Apr | 8 | tar -e02 | Y
M&E | to 20th Apr | 8 | TAR -M20 | Y
M&E | to 20th Apr | 8 | TAR -Building Services and Lighting | Y
M&E | to 20th Apr | 11 | Spec -M44 | Y
M&E | to 20th Apr | 11 | TAR -E19 | Y
M&E | to 20th Apr | 11 | TAR -E02 | Y
M&E | to 20th Apr | 11 | TAR -M40 | Y
M&E | to 20th Apr | 11 | TAR -M44 | Y
M&E | to 20th Apr | 11 | TAR -M12 | Y
proc | to 20th Apr |  | Prepare Enquiry Package - M12 | Y
proc | to 20th Apr |  | Tender Duration - M12 | Y
proc | to 20th Apr |  | Place Order on DEMA - M12
proc | to 20th Apr |  | Tender Duration - M12B | Y
proc | to 20th Apr |  | Place Order on DEMA - M12B
proc | to 20th Apr |  | Place Order on DEMA - M13 | Y
proc | to 20th Apr |  | Place Order on DEMA - M18
proc | to 20th Apr |  | Place Order on DEMA - M20
proc | to 20th Apr |  | Prepare Enquiry Package - M20B | Y
proc | to 20th Apr |  | Tender Duration - M20B | Y
proc | to 20th Apr |  | Tender Duration - M33 | Y
proc | to 20th Apr |  | Place Order on DEMA - M33
proc | to 20th Apr |  | Tender Duration - M40 | Y
proc | to 20th Apr |  | Place Order on DEMA - M40
proc | to 20th Apr |  | Tender Duration - M44 | Y
proc | to 20th Apr |  | Place Order on DEMA - M44
proc | to 20th Apr |  | Place Order on DEMA - M45
proc | to 20th Apr |  | Place Order on DEMA - M60 | Y
proc | to 20th Apr |  | Place Order on DEMA - M62
proc | to 20th Apr |  | Place Order on DEMA - E02
proc | to 20th Apr |  | Place Order on DEMA - E13
proc | to 20th Apr |  | Tender Duration - E17 | Y
proc | to 20th Apr |  | Prepare Enquiry Package - E18 | Y
proc | to 20th Apr |  | Tender Duration - E18 | Y
proc | to 20th Apr |  | Tender Duration - E15 | Y
proc | to 20th Apr |  | Tender Duration - E19
proc | to 20th Apr |  | Place Order on DEMA - E20
proc | to 20th Apr |  | Place Order on DEMA - E21
proc | to 20th Apr |  | Place Order on DEMA - E22
proc | to 20th Apr |  | Prepare Enquiry Package - E26
proc | to 20th Apr |  | Earliest Delivery Date - M05
proc | to 20th Apr |  | Place Order on DEMA - M14
proc | to 20th Apr |  | Tender Duration - M59 | Y
proc | to 20th Apr |  | Place Order on DEMA - M59
proc | to 20th Apr |  | Prepare Enquiry Package - M60.1 | Y
proc | to 20th Apr |  | Place Order on DEMA - M71 | Y
proc | to 20th Apr |  | Place Order on DEMA - M80 | Y
proc | to 20th Apr |  | Prepare Enquiry Package - M64 | Y
proc | to 20th Apr |  | Earliest Delivery Date - M25
proc | to 20th Apr |  | Place Order on DEMA - M31 | Y
proc | to 20th Apr |  | Place Order on DEMA - E06 | Y
proc | to 20th Apr |  | Place Order on DEMA - M19
proc | to 20th Apr |  | Place Order on DEMA - M56
proc | to 20th Apr |  | Place Order on DEMA - M39 | Y
proc | to 20th Apr |  | Place Order on DEMA - M43
M&E | to 25th May | 99 | FDS
M&E | to 25th May | 99 | HazOp Study - Digesters (Area 4)
M&E | to 25th May | 99 | HazOp Study -Steam
M&E | to 25th May | 1 | DS -PST Autodesludging | Y
M&E | to 25th May | 3 | SPEC -Lightning protection installation
M&E | to 25th May | 3 | TAR -Instrumentation - level | Y
M&E | to 25th May | 3 | TAR -Instrumentation - flow | Y
M&E | to 25th May | 3 | TAR -Instrumentation - pressure | Y
M&E | to 25th May | 3 | TAR -Instrumentation - temperature | Y
M&E | to 25th May | 4 | SPEC -Lightning protection installation
M&E | to 25th May | 5 | Detailed Design handover package to site team | Y
M&E | to 25th May | 5 | Detailed Design handover package to commissioning team | Y
M&E | to 25th May | 6 | URS
M&E | to 25th May | 6 | SPEC -Lightning protection installation
M&E | to 25th May | 8 | SPEC -Lightning protection installation
M&E | to 25th May | 11 | SPEC -Lightning protection installation
M&E | to 25th May | 99 | TAR -Electrical Installation - General | Y
M&E | to 25th May | 99 | TAR -Valves - General (M44) | Y
M&E | to 25th May | 1 | TAR -Valves (M44) | Y
M&E | to 25th May | 1 | TAR -PST Auto desludging | Y
M&E | to 25th May | 6 | TAR -Instrumentation - flow | Y
M&E | to 25th May | 6 | TAR -Instrumentation - pressure | Y
M&E | to 25th May | 6 | TAR -Instrumentation - temperature | Y
M&E | to 25th May | 8 | TAR -Instrumentation - flow | Y
M&E | to 25th May | 8 | TAR -Instrumentation - pressure | Y
M&E | to 25th May | 8 | TAR -Instrumentation - temperature | Y
M&E | to 25th May | 8 | TAR -Valves (M44) | Y
M&E | to 25th May | 10 | TAR -SILOXANE REMOVAL PACKAGE PLANT (M56) | Y
M&E | to 25th May | 11 | TAR -Instrumentation - flow | Y
M&E | to 25th May | 11 | TAR -Instrumentation - pressure | Y
M&E | to 25th May | 11 | TAR -Instrumentation - temperature | Y
Civil | to 25th May | 1 | Thickening poly GA | Y
Civil | to 25th May | 3 | HpH surround RCD | Y
Civil | to 25th May | 3 | HpH MCC GA | Y
Civil | to 25th May | 8 | Dewatering Cent GA & RCD | Y
Civil | to 25th May | 8 | Dewatering poly RCD | Y
Civil | to 25th May | 8 | Post-Dig mods | Y
Civil | to 25th May | 9 | LTP Blower | Y
Civil | to 25th May | 9 | LTP Chem storage | Y
Civil | to 25th May | 99 | Pipe Bridge | Y
Civil | to 25th May | 1 | Thickening Centrifuges | Y
Civil | to 25th May | 9 | LTP HX | Y
Civil | to 25th May | 9 | LTP MCC | Y
Civil | to 25th May | 9 | LTP Ductwork & Drainage | Y
proc | to 25th May |  | Earliest Delivery Date - M10
proc | to 25th May |  | Place Order on DEMA - M20 | Y
proc | to 25th May |  | Earliest Delivery Date - M26
proc | to 25th May |  | Place Order on DEMA - M33
proc | to 25th May |  | Place Order on DEMA - M40
proc | to 25th May |  | Place Order on DEMA - M44 | Y
proc | to 25th May |  | Place Order on DEMA - M45
proc | to 25th May |  | Place Order on DEMA - M60 | Y
proc | to 25th May |  | Place Order on DEMA - M62 | Y
proc | to 25th May |  | Place Order on DEMA - E02 | Y
proc | to 25th May |  | Place Order on DEMA - E13
proc | to 25th May |  | Place Order on DEMA - E14
proc | to 25th May |  | Earliest Delivery Date - E14
proc | to 25th May |  | Place Order on DEMA - E15
proc | to 25th May |  | Place Order on DEMA - E16
proc | to 25th May |  | Place Order on DEMA - E17
proc | to 25th May |  | Place Order on DEMA - E18
proc | to 25th May |  | Place Order on DEMA - E19
proc | to 25th May |  | Place Order on DEMA - E20
proc | to 25th May |  | Place Order on DEMA - E21
proc | to 25th May |  | Place Order on DEMA - E22
proc | to 25th May |  | Place Order on DEMA - E23
proc | to 25th May |  | Prepare Enquiry Package - E26
proc | to 25th May |  | Tender Duration - E26
proc | to 25th May |  | Place Order on DEMA - E44
proc | to 25th May |  | Earliest Delivery Date - E44
proc | to 25th May |  | Place Order on DEMA - M60.1 | Y
proc | to 25th May |  | Tender Duration - M64 | Y
proc | to 25th May |  | Earliest Delivery Date - M24
proc | to 25th May |  | Earliest Delivery Date - M03 | Y
proc | to 25th May |  | Earliest Delivery Date - M25 | Y
proc | to 25th May |  | Earliest Delivery Date - M29
proc | to 25th May |  | Place Order on DEMA - E41
proc | to 25th May |  | Place Order on DEMA - M19 | Y
proc | to 25th May |  | Place Order on DEMA - M56 | Y
proc | to 25th May |  | Place Order on DEMA - M12 | Y
proc | to 25th May |  | Place Order on DEMA - M12B | Y
proc | to 25th May |  | Place Order on DEMA - M20B | Y
proc | to 25th May |  | Place Order on DEMA - M26 | Y
proc | to 25th May |  | Tender Duration - E14 | Y
proc | to 25th May |  | Place Order on DEMA - M59 | Y
proc | to 25th May |  | Prepare Enquiry Package - M81 | Y
proc | to 25th May |  | Tender Duration - M81 | Y
proc | to 25th May |  | Place Order on DEMA - M81 | Y
proc | to 25th May |  | Place Order on DEMA - M56 | Y
proc | to 25th May |  | Place Order on DEMA - M43 | Y
Civil | to 29th June |  | overground pipework supports
Civil | to 29th June |  | LTP HX slab | Y
Civil | to 29th June |  | LTP MCC | Y
Civil | to 29th June |  | LTP Settlement tank | Y
Civil | to 29th June |  | LTP RAS/SAS pump slab | Y
Civil | to 29th June |  | LTP Stilling tube
Civil | to 29th June |  | LTP tank mods -Modification Details and Walkway Support Bases | Y
Civil | to 29th June |  | OCU slab -Area 1
M&E | to 29th June |  | TAR -Instrumentation - General | Y
M&E | to 29th June |  | HAZOP | Y
M&E | to 29th June |  | SPEC -Lightning protection installation
M&E | to 29th June |  | TAR -Lightning Protection
proc | to 29th June |  | Earliest Delivery Date - M04
proc | to 29th June |  | Earliest Delivery Date - M13 | Y
proc | to 29th June |  | Earliest Delivery Date - M12
proc | to 29th June |  | Earliest Delivery Date - M10 | Y
proc | to 29th June |  | Earliest Delivery Date - M12B | Y
proc | to 29th June |  | Earliest Delivery Date - M20 | Y
proc | to 29th June |  | Earliest Delivery Date - M20B | Y
proc | to 29th June |  | Earliest Delivery Date - M26 | Y
proc | to 29th June |  | Place Order on DEMA - M33
proc | to 29th June |  | Earliest Delivery Date - M33
proc | to 29th June |  | Place Order on DEMA - M40
proc | to 29th June |  | Earliest Delivery Date - M44 | Y
proc | to 29th June |  | Place Order on DEMA - M45 | Y
proc | to 29th June |  | Earliest Delivery Date - M60
proc | to 29th June |  | Earliest Delivery Date - M62
proc | to 29th June |  | Earliest Delivery Date - E02 | Y
proc | to 29th June |  | Place Order on DEMA - E13 | Y
proc | to 29th June |  | Delivery Date - E13 #1 -GBT & Dewatering feed pumps
proc | to 29th June |  | Place Order on DEMA - E14 | Y
proc | to 29th June |  | Earliest Delivery Date - E14
proc | to 29th June |  | Place Order on DEMA - E15
proc | to 29th June |  | Place Order on DEMA - E16 | Y
proc | to 29th June |  | Earliest Delivery Date - E16
proc | to 29th June |  | Place Order on DEMA - E17 | Y
proc | to 29th June |  | Place Order on DEMA - E18 | Y
proc | to 29th June |  | Place Order on DEMA - E19 | Y
proc | to 29th June |  | Earliest Delivery Date - E19
proc | to 29th June |  | Place Order on DEMA - E20 | Y
proc | to 29th June |  | Place Order on DEMA - E21 | Y
proc | to 29th June |  | Place Order on DEMA - E22 | Y
proc | to 29th June |  | Place Order on DEMA - E23
proc | to 29th June |  | Prepare Enquiry Package - E26
proc | to 29th June |  | Tender Duration - E26
proc | to 29th June |  | Place Order on DEMA - E44 | Y
proc | to 29th June |  | Earliest Delivery Date - E44
proc | to 29th June |  | Earliest Delivery Date - M05 | Y
proc | to 29th June |  | Earliest Delivery Date - M16
proc | to 29th June |  | Earliest Delivery Date - M11 | Y
proc | to 29th June |  | Earliest Delivery Date - M35 | Y
proc | to 29th June |  | Place Order on DEMA - M64
proc | to 29th June |  | Earliest Delivery Date - M24
proc | to 29th June |  | Earliest Delivery Date - M28
proc | to 29th June |  | Earliest Delivery Date - M29
proc | to 29th June |  | Earliest Delivery Date - M30
M&E | to 29th June |  | CE for PST Autodesludging
proc | to 29th June |  | Earliest Delivery Date - E03 (MCC3)
proc | to 29th June |  | Earliest Delivery Date - E03 (MCC4)
proc | to 29th June |  | Earliest Delivery Date - Kiosk (MCC#4) | Y
proc | to 29th June |  | Earliest Delivery Date - Kiosk (MCC#3) | Y
proc | to 29th June |  | Earliest Delivery Date - Kiosk (MCC#2) | Y
proc | to 29th June |  | Earliest Delivery Date - M19
proc | to 29th June |  | Earliest Delivery Date - M48
proc | to 29th June |  | Earliest Delivery Date - M39
Civil | to 27th July |  | Blower building wall mods
Civil | to 27th July |  | RL PS wet well
Civil | to 27th July |  | SHT OCU base
M&E | to 27th July |  | Review/approval of Supplier drawings - M33
M&E | to 27th July |  | Review/approval of Supplier drawings - M62
M&E | to 27th July |  | Lightning protection installation
M&E | to 27th July |  | Review/approval of Supplier drawings - M59
M&E | to 27th July |  | Review/approval of Supplier drawings - M31 | Y
M&E | to 27th July |  | Review/approval of Supplier drawings - M56
M&E | to 27th July |  | Prepare Supplier drawings for approval - M41
M&E | to 27th July |  | Review/approval of Supplier drawings - M43
proc | to 27th July |  | Earliest Delivery Date - M04 | Y
proc | to 27th July |  | Earliest Delivery Date - M18 | Y
proc | to 27th July |  | Place Order on DEMA - M33 | Y
proc | to 27th July |  | Place Order on DEMA - M40
proc | to 27th July |  | Earliest Delivery Date Area 3 (first delivery) -M44 | Y
proc | to 27th July |  | Earliest Delivery Date - M60
proc | to 27th July |  | Delivery Date - E13 #2 -Strainpress & thickening feed, HpH, Dig, Boiler feed, Liquor return to HoW | Y
proc | to 27th July |  | Earliest Delivery Date - E14
proc | to 27th July |  | Place Order on DEMA - E15 | Y
proc | to 27th July |  | Earliest Delivery Date - E17 | Y
proc | to 27th July |  | Urgetn part-shipment delivery -E20
proc | to 27th July |  | Prepare Enquiry Package - E26
proc | to 27th July |  | Earliest Delivery Date - E44
proc | to 27th July |  | Earliest Delivery Date - M14 | Y
proc | to 27th July |  | Earliest Delivery Date - M59
proc | to 27th July |  | Earliest Delivery Date - M81 | Y
proc | to 27th July |  | Earliest Delivery Date - M80 | Y
proc | to 27th July |  | Place Order on DEMA - M64 | Y
proc | to 27th July |  | Earliest Delivery Date - M30
proc | to 27th July |  | Earliest Delivery Date - E10 (LV Dis) | Y
proc | to 27th July |  | CE for PST Autodesludging | Y
proc | to 27th July |  | Earliest Delivery Date - E03 (MCC3)
proc | to 27th July |  | Earliest Delivery Date - E03 (MCC4)
proc | to 27th July |  | Earliest Delivery Date - M19 | Y
proc | to 27th July |  | Place Order on DEMA - M41 | Y
proc | to 27th July |  | Earliest Delivery Date - M43
proc | to 31st Aug |  | Earliest Delivery Date - M06
proc | to 31st Aug |  | Earliest Delivery Date - M33
proc | to 31st Aug |  | Place Order on DEMA - M40
proc | to 31st Aug |  | Earliest Delivery Date Area 3 (last delivery) -M44
proc | to 31st Aug |  | Earliest Delivery Date - M45
proc | to 31st Aug |  | Earliest Delivery Date - M60 | Y
proc | to 31st Aug |  | Earliest Delivery Date - E15
proc | to 31st Aug |  | Earliest Delivery Date - E20
proc | to 31st Aug |  | Earliest Delivery Date - E21
proc | to 31st Aug |  | Earliest Delivery Date - E22
proc | to 31st Aug |  | Earliest Delivery Date - E23
proc | to 31st Aug |  | Prepare Enquiry Package - E26 | y
proc | to 31st Aug |  | Earliest Delivery Date - E44
proc | to 31st Aug |  | Earliest Delivery Date - M59
proc | to 31st Aug |  | Place Order on DEMA -M44.1 (Actuated Valves) | y
proc | to 31st Aug |  | Earliest Delivery Date - M60.1 (Blower) | y
proc | to 31st Aug |  | Earliest Delivery Date - M64
proc | to 31st Aug |  | Earliest Delivery Date - M30 | y
proc | to 31st Aug |  | Earliest Delivery Date - E03 (MCC3) | y
proc | to 31st Aug |  | Earliest Delivery Date - E03 (MCC4) | y
proc | to 31st Aug |  | Earliest Delivery Date - M56 | Y
proc | to 31st Aug |  | Earliest Delivery Date - M41 | y
Civil Site | to 31st Aug | 1 | Construct tanker import bays (C02) -Thickening Centrifuge Poly (Gang2)
Civil Site | to 31st Aug | 1 | T3 Pipe supports
Civil Site | to 31st Aug | 1 | New scope: Repair of Tank 4 (SUB) | y
Civil Site | to 31st Aug | 1 | Civils - Tanker Import facility (C02) (Gang2)
Civil Site | to 31st Aug | 1 | Civils - pipe support plinths (centrifuge feed) (C02) (Gang2)
Civil Site | to 31st Aug | 1 | Civils - Poly Silo Bund (C02) (Gang2) | y
Civil Site | to 31st Aug | 1 | Civils -OCU base slab (C02) (Gang2)
Civil Site | to 31st Aug | 3 | Mixing pump Plinths (C02) (Bells) | y
Civil Site | to 31st Aug | 3 | HPH Feed Pipebridge FRC (Bells) | y
Civil Site | to 31st Aug | 6 | Civils - Natural Gas supply pipe (M69) (SUB) | y
Civil Site | to 31st Aug | 6 | Civils -Boiler House mods (ventilation penetrations) (BLD1)
Civil Site | to 31st Aug | 6 | Ciivls -pipe support FRC (Bells)
Civil Site | to 31st Aug | 7 | Cross site ductwork (Gang 3) | y
Civil Site | to 31st Aug | 8 | Civils -Conveyor support plinths -FRC (Bells) | y
Civil Site | to 31st Aug | 9 | glycerol specialist coating | y
Civil Site | to 31st Aug | 9 | causting specialist coating | y
Civil Site | to 31st Aug | 9 | Civils -Shower FRC (Bells) | y
Civil Site | to 31st Aug | 11 | Misc Plinths FRC (Bells) | y
Civil Site | to 31st Aug | 13 | SHT Odour Control bases (2nr) (C02) -Gang 3 | y
M&E Site | to 31st Aug | 1 | Mech Install - pipework from Strainpresses to T3 (M12B) (M44) | y
M&E Site | to 31st Aug | 1 | Mech Install -pipework for HpH Centrifuge PS feed (M12B, M44)
M&E Site | to 31st Aug | 1 | Elec Install - Strainpress Feed Pumps (E02, E13)
M&E Site | to 31st Aug | 1 | T4 to Strainpress Feed Pumps pipework (M12B)
M&E Site | to 31st Aug | 1 | Mech Install - Strainpress Feed Pumps (M13) (M12B)
M&E Site | to 31st Aug | 1 | Mech Install - pipework from T5 to Strainpress Feed pumps (M12B) (M44)
M&E Site | to 31st Aug | 1 | Mech Install Blower M60.1
M&E Site | to 31st Aug | 1 | Install PST Autodesludging Pumps M81 (M12)
M&E Site | to 31st Aug | 1 | Mech Install - Centrifuge Feed Pumps (M13)
M&E Site | to 31st Aug | 1 | Pipework to & from SAS thickening feed pumps (M12B)
M&E Site | to 31st Aug | 1 | Pipework from SAS transfer pumps to Tanks 4 & 5 (M12B)
M&E Site | to 31st Aug | 1 | Elec Install - SAS Thickening Feed Pumps (E02, E13)
M&E Site | to 31st Aug | 1 | Elec Install - Thickened SAS Pumps
M&E Site | to 31st Aug | 1 | Mech Install - Centrifuges (2 nr) (M04) | y
M&E Site | to 31st Aug | 1 | Mech Install - centrate pumps (M12B) (M44)
M&E Site | to 31st Aug | 1 | Mech Install - Cake Blending pumps (M14)
M&E Site | to 31st Aug | 1 | Mech Install - cake dilution pumps (M13)
M&E Site | to 31st Aug | 3 | Access Metalwork all tanks (M20) | y
M&E Site | to 31st Aug | 3 | Pipe Bridge 2 (Area 1 to HpH) | y
M&E Site | to 31st Aug | 5 | Mech Install M12 -Area 5 Pipework
M&E Site | to 31st Aug | 6 | Mech Install M65 - Hot Water De Aerator | y
M&E Site | to 31st Aug | 6 | Mech Install - Natural Gas Supply (M69)
M&E Site | to 31st Aug | 6 | Mech Install M20 - Flue Platform & ladder, Header tank support | y
M&E Site | to 31st Aug | 6 | Mech Install M30 - Boiler water feed tank
M&E Site | to 31st Aug | 6 | Mech Install M31 -Boiler Water Chem Dosing system
M&E Site | to 31st Aug | 6 | Mech Install M38 - Safety Shower (M38)
M&E Site | to 31st Aug | 6 | Install Flue Ducting (M25) | y
M&E Site | to 31st Aug | 7 | Pull in LV feed: LVDB to MCC#4
M&E Site | to 31st Aug | 7 | Install MCC#2 | y
M&E Site | to 31st Aug | 7 | Pull in LV sub-feed: LVDB to MCC#2 | y
M&E Site | to 31st Aug | 7 | Install MCC#3 | y
M&E Site | to 31st Aug | 7 | Install MCC#4 | y
M&E Site | to 31st Aug | 8 | Mech Install M60 - Post-digestion tank: blowers (M12)
M&E Site | to 31st Aug | 8 | Mech Install M04 - Centrifuge | y
M&E Site | to 31st Aug | 8 | Mech Install M19 - Centrate Pumps (M19)
M&E Site | to 31st Aug | 9 | Stilling Tube | y
M&E Site | to 31st Aug | 9 | Glycerol Storage Tank | y
M&E Site | to 31st Aug | 9 | Dosing Pump Cabinets | y
M&E Site | to 31st Aug | 9 | Caustic Storage Tank | y
M&E Site | to 31st Aug | 9 | Dosing Tank Access Steelwork | y
M&E Site | to 31st Aug | 9 | Half bridge Scraper | y
M&E Site | to 31st Aug | 9 | Submersible Mixers | y
M&E Site | to 31st Aug | 9 | Heat Exchanger | y
M&E Site | to 31st Aug | 9 | Blowers | y
M&E Site | to 31st Aug | 9 | Recycle Pumps | y
M&E Site | to 31st Aug | 9 | Sludge Pumps | y
M&E Site | to 31st Aug | 9 | Access Stairs | y
M&E Site | to 31st Aug | 9 | Aeration System
M&E Site | to 31st Aug | 9 | Recycle RAS/SAS Pipework
M&E Site | to 31st Aug | 9 | Dosing Pipework
M&E Site | to 31st Aug | 9 | Cable Containment & Cabling
M&E Site | to 31st Aug | 11 | Mech Install: Self Cleaning Filters (M39) (M12) | y
M&E Site | to 31st Aug | 11 | Mech Install: Water Booster Set (M41)
M&E Site | to 31st Aug | 1 | Temp recommissioning of SHT#3 as Digester feed (STAGE B) | y
M&E Site | to 31st Aug | 1 | Decommission existing tank operation SHT#4 (STAGE B) | y
M&E Site | to 31st Aug | 8 | Decommission Blend Tank 1

## Mothly Milestones
Milestone | Last Month | Current Forecast | Slippage (wks) | Comments
Install MCCs 3 & 4 | 2012-08-06 | 2012-08-22 | 2.2857 | Additional items added to MCC4 late on
Repair Sludge Holding Tank 4 | 2012-08-30 | 2012-09-03 | 0.57143 | Impacted by poor weather.
Access stelwork for HpH tanks | 2012-08-16 | 2012-08-13 | -0.42857
Recommission Sludge Holding Tank 3 as digester feed | 2012-08-08 | 2012-08-13 | 0.71429 | Lack of resources from mech installer (holidays)
Install Centrifuges | 2012-08-10 | 2012-08-17 | 1 | Weather delayed completion of civils prior to install

## Summary Data
| 2010-09-01 | 2010-10-01 | 2010-11-01 | 2010-12-01 | 2011-02-01 | 2011-03-01 | 2011-04-01 | 2011-05-01 | 2011-06-01 | 2011-07-01 | 2011-08-01 | 2011-09-01 | 2011-10-01 | 2011-11-01 | 2011-12-01 | 2012-01-01 | 2012-02-01 | 2012-03-01 | 2012-04-01 | 2012-05-01 | 2012-06-01 | 2012-07-01 | 2012-08-01 | Key Activities This Month |  |  | Key Activities Next Month
Planned Value | [6 empty] | 722178 | 1077401 | 1451729 | 1869907 | 2387131 | 3155936 | 3791533 | 4601174 | 5151772 | 6789343 | 8906708 | 9900803 | 10317617 | 10926341 | 11571365 | 11862084 | 12191328 | Activity | Planned Progress | Actual Progress | Activity | Planned Progress
Earned Value | [6 empty] | 708964 | 963556 | 1194865 | 1407544 | 1635505 | 1862380 | 2164740 | 2433621 | 2607399 | 2871884 | 3204579 | 3928602 | 4596339 | 5552542 | 6362479 | 8003078 | 9155993 | Control PLC manufacturing -BAS | Complete | Complete
Actual Cost | [6 empty] | 780703 | 797375 | 1022578 | 1161456 | 1338140 | 1485713 | 1735918 | 1879572 | 1980210 | 2199080 | 3582231 | 4322341 | 4839812 | 5989434 | 6623178 | 8265892 | 9325712 | Gas Holder base formwork -CQ | Complete | Complete | Commissioning -Bas | Complete
SPI | 1 | 1 | 1 |  |  | 1 | 0.9817 | 0.89433 | 0.82306 | 0.75273 | 0.68513 | 0.59012 | 0.57094 | 0.52891 | 0.50612 | 0.423 | 0.35979 | 0.3968 | 0.44548 | 0.50818 | 0.54985 | 0.67468 | 0.75103 | HV Cabling (EDF) -Col | Complete | Not Started | Commissioning -CQ | Complete
CPI | [6 empty] | 0.90811 | 1.2084 | 1.1685 | 1.2119 | 1.2222 | 1.2535 | 1.247 | 1.2948 | 1.3167 | 1.3059 | 0.89458 | 0.90891 | 0.94969 | 0.92706 | 0.96064 | 0.96821 | 0.9818
Target | [23 empty] | Gas Holder slab -Col | Complete | 50% Complete | Commissioning -Col | Complete | bar: 2010-09-01 to 2012-08-01
[5 empty] | 2011-02-01 | 2011-03-01 | 2011-04-01 | 2011-05-01 | 2011-06-01 | 2011-07-01 | 2011-08-01 | 2011-09-01 | 2011-10-01 | 2011-11-01 | 2011-12-01 | 2012-01-01 | 2012-02-01 | 2012-03-01 | 2012-04-01 | 2012-05-01 | 2012-06-01 | 2012-07-01 | 2012-08-01
[27 empty] | Commissioning -Cam | Complete
Overall Project Completion |  |  |  |  | 2012-09-21 | 2012-09-21 | 2012-10-04 | 2012-11-20 | 2012-10-28 | 2012-11-15 | 2012-10-31 | 2013-01-14 | 2012-11-29 | 2012-12-07 | 2013-01-11 | 2013-01-11 | 2013-02-12 | 2013-01-08 | 2013-01-07 | 2012-12-19 | 2013-01-03 | 2013-01-14 | 2013-01-31
Probabalistic Project Completion (P50) |  |  |  |  | 2011-11-01: 2013-02-20; 2011-12-01: 2013-02-25; 2012-01-01: 2013-03-15; 2012-02-01: 2013-05-15; 2012-03-01: 2013-05-15; 2012-04-01: 2013-05-15; 2012-05-01: 2013-05-15; 2012-06-01: 2013-05-15; 2012-07-01: 2013-02-13; 2012-08-01: 2013-03-11
Probabalistic Project Completion (P80) |  |  |  |  | 2011-11-01: 2013-04-02; 2011-12-01: 2013-04-03; 2012-01-01: 2013-04-29; 2012-02-01: 2013-06-25; 2012-03-01: 2013-06-25; 2012-04-01: 2013-06-25; 2012-05-01: 2013-06-25; 2012-06-01: 2013-06-25; 2012-07-01: 2013-03-11; 2012-08-01: 2013-04-04
%age Activities completed on time or early | [6 empty] | 12.05% | 30.56% | 92.73% | 100% | 32.89% | 7.273% | 5.936% | 8.163% | 49.56% | 24.54% | 45% | 47.2% | 65.69% | 63.33% | 50% | 43.24% | 49.48%
Target |  |  |  |  | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75%