Programme Delays to process plant upgrade projects –Lessons learnt

July 12

- Get Mech Installer on board ASAP. –Consider use of LOI, staged release of scope / design info, etc. Ensure they are prioritising the critical activities from day 1.

- Drive for early completion of P&IDs and HAZOPs, to minimise late design changes

- Potential programme delays should be actively understood before decisions are made on design / scope changes

- Delivery times & design assumptions/preferences need to be considered as well as cost when selecting suppliers

- Some suppliers / subcontractors start their leadtime from issuing of an order number. Others from receipt of signed subcontract. Others may require payment up front. Ensure this is understood & agreed during tender negotiations.

- Don’t underestimate design resources required. –it is better to have some under-utilisation of design resources than programme delays (and associated additional prelims) from over-utilisation.

- Don’t let disputes with Owner’s technical assurance team drag on. Drive for a resolution. Uncertainties around scope or standards can be debilitating.

- Get an early understanding of interfaces with existing processes, and the timescales for developing & approving impact plans.

- Ensure design team understand & agree priorities.

- Ensure regular (weekly) design & procurement progress meetings are well attended & chaired. Consider utilising Lean “Last planner” templates

- Ring-fenced design resources for each project. Or if not possible, ensure there is only 1 person who can re-task a shared resource

- Spend the time upfront to ensure design processes are robust and slick –doc control, release of M&E info to civils, management of assumptions, approval of supplier drgs, scope management. –These have all caused problems on recent projects.

- 3D modelling can be a bottleneck –ensure right quantity & quality of CAD people are available at the right time.

- Spreadsheets have proved a poor method of tracking & reporting design progress. –Progress meetings are a better method.

- If re-using existing assets, get a good understanding of their condition and Ops’ handover requirements early on. –Ops’ requirements can often be challenged.

- A strong design presence on site can nip a lot of potential problems in the bud.

- A flexible and accommodating Mech Install subcontractor is worth paying a premium for. –Same goes for Elec Install.

- Critical path is likely to be driven by mech install, elec install, and/or MCC (and associated software). –Additional focus and effort needs to be put into understanding & driving these sub-programmes. Before, during and after procurement of the subcontracts.