## Summary
Project Control Systems Questionnaire
Organization:
Location:
Date of Assessment:
Contacts:
Owner:
Organization
Comments
1.
2.
3.
4.
5.
6.
7.
8.
9.
10.

## Estimating
Assessment of Project Control Systems
| Organization: | 0
| Location: | 0
| Date: | 0
| Topic of Interest | Discussion
1.0 | Estimating
1.1 | Are formal Estimate Plans prepared with a schedule?
1.2 | Are required inputs defined by level (concept, preliminary, detail, etc.) of estimate?
1.3 | Is a standard Code of Accounts used (e.g.CSI)?
1.4 | Is the standard Lilly Estimate Summary used?
1.5 | Are standard estimating templates used for:
- Civil and Structural
- Mechanical (HVAC)
- Mechanical (Utilities and Plumbing)
- Electrical
- Instrumentation and Control
- VDS
- Fire Protection
- Process Equipment
- Process Piping
- Professional Services
- General Conditions
- Commissioning & Qualification
- AFU
- Lilly Costs
1.6 | What metrics/price sources are used for direct costs?
1.7 | Are Indirect Cost elements factored, or are they developed from bottom-up calculations?
1.8 | Are Professional Services costs factored, or are they developed from bottom-up calculations?
1.9 | What historical cost databases are maintained?
1.10 | Is a formal estimate basis prepared?
1.11 | Are all estimates subject to formal reviews before presentation?
1.12 | Are CM costs (including General Conditions) estimated based on a time-phased execution plan?

## Reporting
Assessment of Project Control Systems
| Organization: | 0
| Location: | 0
| Date: | 0
| Topic of Interest | Discussion
2.0 | Reporting
2.1 | Is a formal status report issued on a regular basis? Is there an established distribution matrix for reports?
2.2 | Does the report include:
- Executive Summary?
- Areas of Concern?
- Earned Progress Curves?
- Cost Section?
- Schedule Section?
- Change Management Section?
2.3 | Executive Summary contents:
- Concise?
- Contains all relevant issues?
2.4 | Areas of Concern contents:
- Current?
- Complete?
- Include recommended mitigation?
- Include projected impacts?
2.5 | Earned Progress Curves:
- Show plan (early start)?
- Show actual earned progress?
- Show forecast progress?
- Overall or component curves?
- Productivity analysis (cumulative and ETC)?
2.6 | Cost Section contents:
- H.O. Cost report showing original budget, current budget, actual cost (period and to-date), ETC, budget variance, contingency, pending changes?
- Field Cost report showing same details as H.O. report plus commitments, uncommitted, allowances for growth?
- Risks and Opportunities table showing possible exposures not yet in forecasts? Does this include analysis of contingency by account?
- Cash flow and commitment curves?
- A TIC Trend report (before Stage Gate 2)?
- Narrative discussion of cost reports?
2.7 | Schedule Section contents:
- Level 1 Milestone schedule?
- Level 2 Discipline/System?
- Resource tracking histograms (by discipline, overall craft, major subcontractor)?
- Narrative discussion of schedule and critical path?
2.8 | Change Management Section contents
- Change Management Log(s)?

## Change Management
Assessment of Project Control Systems
| Organization: | 0
| Location: | 0
| Date: | 0
| Topic of Interest | Discussion
3.0 | Change Management
3.1 | Is there a formal written change management procedure? Is it followed? Is it project specific?
3.2 | Is the change process a one step (CO), two step (PCN,CO) or three step (internal CN, PCN, CO) effort?
3.3 | Who is responsible for identification of potential changes?
3.4 | Who decides whether changes are presented to Lilly?
3.5 | Are changes presented with cost and schedule impacts?
3.6 | What is target timing for processing changes?
3.7 | What accuracy are the estimates included with change notifications?
3.8 | Are changes tracked by root causes (design error, fabrication error, Lilly change, etc.)?
3.9 | Are change notification turnaround times tracked?
3.10 | Are web-based or automated tools used for change notifications (ProLog, PMWeb, Oracle Unifier, etc.)?
3.11 | What change controls are used for subcontracts and purchase orders? Who is responsible for managing this effort?
3.12 | Once a change is dispositioned, How long does it take to incorporate it in the budget? In the forecast?
3.13 | When are changes incorporated in the forecast?
3.14 | Are all pending changes incorporated in the Risks and Opportunities Report?

## Progress Measurement
Assessment of Project Control Systems
| Organization: | 0
| Location: | 0
| Date: | 0
| Topic of Interest | Discussion
4.0 | Progress Measurement
4.1 | Does a written procedure exist for progress measurement? Is it used? Is it project specific?
4.2 | Is an Earned Value system used on all projects?
4.3 | How is Earned Value linked to the scheduling tool? To the cost tool?
4.4 | Is partial progress permitted between milestones?
4.5 | How are the weights assigned to intermediate milestones?
4.6 | How are the weights assigned to activities?
4.7 | Who assesses physical progress?
4.8 | Is claimed progress challenged, tested or independently verified?
4.9 | Is productivity regularly calculated, graphed, reported and analyzed?
4.10 | At what point are changes incorporated into the progress system? What approvals are required?
4.11 | Are "level of effort" activities used appropriately?
4.12 | How is progress of construction/subcontractors measured? Is this linked to payment approvals?
4.13 | How is the progress measurement system linked to the cost and schedule forecasts?
4.14 | Is productivity ETC reported?

## Cost Control
Assessment of Project Control Systems
| Organization: | 0
| Location: | 0
| Date: | 0
| Topic of Interest | Discussion
5.0 | Cost Control
5.1 | Does a written procedure exist for cost control? Is it used? Is it project specific?
5.2 | How is the cost control system linked to the accounting system?
5.3 | How is data integrity assured between the accounting system and the cost control system? What is the frequency of reconcilliation?
5.4 | What code of accounts is used within the cost control system? Is it compatible with the Lilly SAP WBS? Can the system matrix to another set of codes?
5.5 | How are the budgets loaded from the estimates?
5.6 | Can costs which are outside the contractor's system (e.g. Lilly costs) be incorporated into the cost control system if requested?
5.7 | Are cost and commitment curves available? Do they include plan, actual and forecast?
5.8 | What is the process for developing forecasts? If embedded algorithms are used, what are they, and what audits are made to assure they are reviewed?
5.9 | How is budget information provided to Supply Management for PO's and subcontracts? What is the role of Project Control in the bid & award process?
5.10 | Are material quantities trended? What is the frequency of quantity reporting of major commodities? Who is responsible for ensuring early identification of variations from budgets?
5.11 | Before the detailed control budget is available, is the project TIC trended?
5.12 | Is a Risks and Opportunities log maintained for cost exposures not yet included in the forecast?
5.13 | How is contingency managed?
5.14 | How are budget transfers managed?
5.15 | How are non-scope changes (deviations) managed?

## Planning
Assessment of Project Control Systems
| Organization: | 0
| Location: | 0
| Date: | 0
| Topic of Interest | Discussion
6.0 | Planning
6.1 | Does a written procedure exist for planning? Is it used? Is it project specific?
6.2 | Is a structured method (e.g. Interactive Planning) used for developing the project plan?
6.3 | Does the planning process incorporate phases outside the contractor's workscope (e.g. Qualification)?
6.4 | Do all stakeholders participate in the planning process?
6.5 | Is a CPM tool (Primavera P6, MSProject, etc.) used for all project scheduling?
6.6 | How are schedule constraints defined, verified and communicated? How is the schedule validated?
6.7 | How is the project schedule integrated between participants?
6.8 | How is buy-in to the project schedule by all participants (including subcontractors and suppliers) achieved?
6.9 | To what extent is the schedule resource loaded?
6.10 | How is the critical path defined (<0 float, <5 days float, etc.) Are critical activity reports generated?
6.11 | Are Monte Carlo type simulations used on the schedule?
6.12 | Is the project schedule coded to allow reports by discipline, area, subcontract/bid package, qualification system, etc.?
6.13 | Is the project schedule distributed to and used by all project participants?
6.14 | Are documentation needs included in the schedule?
6.15 | Are there planned timeframes for developing more detailed schedules (e.g. Level 2 into Level 3)?

## Schedule Control
Assessment of Project Control Systems
| Organization: | 0
| Location: | 0
| Date: | 0
| Topic of Interest | Discussion
7.0 | Schedule Control
7.1 | Does a written procedure exist for schedule control? Is it used? Is it project specific?
7.2 | What is the frequency of schedule statusing? Who is responsible?
7.3 | What is the frequency of schedule reporting?
7.4 | How are forecasts developed?
7.5 | Are Look Ahead reports provided? If so, to whom and within what parameters (e.g. 2 weeks before to 3 weeks after)
7.6 | Are the schedules and reports used? Who uses them?
7.7 | What is the process for handling negative float, critical and near-critical activities?
7.8 | What is the process for resource leveling as the schedule changes?
7.9 | How is schedule analysis performed, and how are the results communicated to the relevant parties?
7.10 | How are the schedule effects of changes evaluated and incorporated into to schedule?

## Document Control
Assessment of Project Control Systems
| Organization: | 0
| Location: | 0
| Date: | 0
| Topic of Interest | Discussion
8.0 | Document Control
8.1 | Does a written procedure exist for document control? Is it used? Is it project specific?
8.2 | What system is used to manage documents?
8.3 | Do documents reside within the document management system? As scanned files? As native files?
8.4 | What documents are handled within the system? All documents? Vendor documents?
8.5 | Are reports available that report document status compared with plans? Are they used?
8.6 | How are document requirements communicated to suppliers and subcontractors?
8.7 | What mechanisms are in place to verify that documents are complete, correct and appropriate?
8.8 | How are IFC subcontract packages controlled relative to changes?
8.9 | What is the reporting structure for document control (engineering, procurement, construction, project control, other)
8.10 | What is the process used to assure that documents are being distributed to all interested parties? What controls are in place for additions and deletions to the distribution matrices?